## Risk Register
[6 empty] | RISK REGISTER |  |  |  |  | Project Name:
Date:
| RISK TYPE & RISK EVENT | Likelihood of Occurrence (L) | Severity (S) | Risk Ranking | Areas Impacted | Approximate Schedule Impact (months) | Potential Cost Impact | Lead Responsibility | Design Discipline Affected | Risk Assesment |  |  | Probable Cost of Mitigation | Potential Cost Impact after Mitigation | Likelihood of Occurrence after Mitigation (L) | Severity after Mitigation (S) | Risk Ranking After Mitigation
|  | 1. Very low 2. Low 3. Moderate 4. High 5. Very High | 1 2 3 4 5 | L x S | S - Schedule C - Cost H - Safety/Health O - Other |  |  | 1. District 2. Design Team/ Consultant 3. Other | G - Geotechnical C - Civil A - Architectural S - Structural H - HVAC P - Plumbing E - Electrical PM - Process Mech. PE - Process Engineering I&C - Instruct. & Controls | Risk Control Measures in Design or Mitigation |  | Residual Risks
No. | [16 empty] | L x S
Regulatory
Planning and Design
Financial / Commercial / Contractual
Logistics / Access
Construction
Environmental
0
| Safety and Security | [15 empty] | 0
Operations

## Severity Categories
Severity Categories
Score | Health, Safety & Environmental Impact | Financial Impact | Operation Impact
1 | - Minor Injuries/ Inconvieniences |  | - Minor revenue loss
| - Operative can continue work | - $1000's additional cost | - Public relations embarrassement
- Short term local damage
2 | - Minor Injuries |  | - Significant revenue loss
| - Operative Requireds First Aid Treatment | - $10,000's additional cost | - Minor security alert
| - Stops Work |  | - Re-routing local access
- Medium term local damage or short tem regional damage
3 | - Reportable/Lost Time Inurty or Illness | - Project Delay of several weeks | - Effects of a facility closure
| - Long term local damage | - $100's K additional cost | - Major regional impact
4 | - Major injury or illness with long term effects | - Project Delay of several months | -Major effects to infrastructure
| - Long term systematic damage | - $1M's additional cost
5 | - Fatalities | - Potentiona to close down the project | -Loss of functionality
- Permanent damage

## Instructions
INSTRUCTIONS ON HOW TO COPY THIS TEMPLATE
PLEASE NAVIGATE TO FILE THEN CLICK ON MAKE A COPY (SEE ATTACHED IMAGE BELOW)