## Project Template
Step 1: Risk Identification | [8 empty] | Step 2: Risk Assessment | [10 empty] | Step 3: Risk Response |  |  |  |  | Step 4: Monitor & Control
[8 empty] | Rank |  |  | Cost Impact ($M) |  |  |  |  | Schedule Impact (Weeks)
# | Category | Phase | Opportunity / Threat | Risk | Risk Name | Detailed Description | P6 Work Package or Activity Related to Risk | Probability (1 - 5) | Consequence (1-5) | Severity (Priority) | Probability (%) | Minimum (@10%) | Most Likely Cost ($M) | Maximum (@90%) | COST IMPACT | Minimum | Most Likely (no. of weeks) | Maximum | TIME IMPACT (Weeks) | Response Category | Administration Notification | Response | Risk Owner | Contingency Plan | Status | Date Last Updated | Tracking Comments
1 |  | Design |  | Risk | [5 empty] | 0 |  | 5 |  |  | 0 |  |  |  | 0 |  | Yes
2 |  | Construction |  | Risk | [5 empty] | 0 |  |  |  |  | 0 |  |  |  | 0 |  | No
3 |  | Planning/Scoping |  | Risk | [5 empty] | 0 |  |  |  |  | 0 |  |  |  | 0 |  | Yes
4 |  | Design-Constructin |  | Issue | [5 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
5 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
6 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
7 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
8 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
9 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
10 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
11 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
12 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
13 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
14 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
15 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
16 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
17 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
18 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
19 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
20 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
21 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
22 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
23 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
24 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
25 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
26 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
27 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
28 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
29 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
30 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
31 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
32 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
33 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
34 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
35 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
36 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
37 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
38 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
39 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
40 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0
41 | [9 empty] | 0 |  |  |  |  | 0 |  |  |  | 0

## Guide
General Tips
1. Utilize the drop down menus when available to keep things consistent
2. Use “Alt + Enter” to place a hard return within a cell. Using a hyphen “-“ as a bullet at the beginning of text along with a hard return at the end of text helps keep information organized when there is more than one response plan or owner.
| Description of risk Register column. | Helpful Hints for risk Assessment
No.: | Identification number of each risk. | Once risks are identified, they should be given a unique identification number, beginning with 1.
Date ID: | The date that the risk was originally identified and included in the risk register.
Date Updated: | The date that the risk was last updated in the risk register.
Project: | The name of the project. | The name used should be consistent for each project.
Category: | The primary category or functional area that the risk pertains to. | Generally, the risk breakdown structure is a way of categorizing or grouping risks by the potential cause of the risk.
SubCategory | The second level of the RBS. | The RBS Group 2 is a more detailed grouping of a particular risk than RBS Group 1.
Opportunity/Threat:
Opportunity | Risk identified as an opportunity in the assessment section of the risk register
Threat | Risk identified as a threat in the assessment section of the risk register
Opp./Threat | Risk identified as an opportunity and a threat in the assessment section of the risk register
Summary Description: | Brief, generally unique description of the risk specific to the Project | In the identification process, think about risks relevant to the project scope, schedule, or cost. Additionally think of risks that may impact the agency's reputation.
Detailed Description: | Detailed description of the risk, generally including a "cause", possible "risk event", and "effects". | The goal is to ensure that other users of the register can interpret the risk identified. Try to be specific and not overly vague. Sample risk statement templates are "If <uncertain event> --> then <effect on objectives>." or "Due to <definite cause>, <uncertain event> may occur, resulting in <effect on objectives>.
Probability: | A rating on a scale of 1 through 5 indicating the likelihood that a risks will occur based on current requirements or conditions. See "Opportunity - Rating Desc." and "Threat - Rating Desc." tabs.
Project Impact (pre-response): | Impacts to project objectives of quality, cost, and time. The pre-response rating is based on current requirements or conditions, prior to the response plan being implemented. | See "Opportunity - Rating Desc." and "Threat - Rating Desc." tabs for general rating definitions to be used as guidance; however this is also subject to judgment of the project team.
Severity (P): | The product of the probability and the highest rated project risks impact
Agency Impact (pre-response): | Impacts to MnDOT's goals of safety, connectivity, congestion, and best-in-class agency (reputation, public perception, etc...). The pre-response rating is based on current requirements or conditions, prior to the response plan being implemented. | See "Opportunity - Rating Desc." and "Threat - Rating Desc." tabs for general rating definitions to be used as guidance; however this is also subject to judgment of the project team.
Severity (A): | The product of the probability and the highest rated agency risks impact
Severity (max): | The absolute value of the highest rated project and agency risks severity value - used primarily for sorting and normally hidden in reporting.
Probability: | The estimated likelihood in percent (%) of the risk occurring based on current state of the risk. For the initial risk assessment, this value should generally correlate with the pre-response assessment. For subsequent risk assessments as response plans are implemented, the value should reflect the estimated probability at the time of assessment.
Minimum (Cost) | The estimated minimum cost impact of the risk if it were to occur (in millions of dollars). For the initial risk assessment, this value should generally correlate with the pre-response assessment. For subsequent risk assessments as response plans are implemented, the value should reflect the estimated impact at the time of assessment.
Most Likely (Cost): | The estimated most likely cost impact of the risk if it were to occur (in millions of dollars). For the initial risk assessment, this value should generally correlate with the pre-response assessment. For subsequent risk assements as response plans are implemented, the value should reflect the estimated impact at the time of assessment.
Maximum (Cost) | The estimated maximum cost impact of the risk if it were to occur (in millions of dollars). For the initial risk assessment, this value should generally correlate with the pre-response assessment. For subsequent risk assessments as response plans are implemented, the value should reflect the estimated impact at the time of assessment.
Minimum (Schedule) | The estimated minimum schedule impact of the risk if it were to occur (in months). For the initial risk assessment, this value should generally correlate with the pre-response assessment. For subsequent risk assessments as response plans are implemented, the value should reflect the estimated impact at the time of assessment.
Most Likely (Schedule): | The estimated most likely schedule impact of the risk if it were to occur (in months). For the initial risk assessment, this value should generally correlate with the pre-response assessment. For subsequent risk assessments as response plans are implemented, the value should reflect the estimated impact at the time of assessment.
Response Category:
Opportunity or Threat Response - Pick One
Accept | Indicates that the project team has decided not to change the project plan to deal with a risk, or is unable to identify any other suitable response strategy. It should be noted, that mitigation or transference is not necessary for all risk threats, particularly those with a small severity rating. Judgment must be used as to whether a more rigorous (and potentially costly) response should be implemented. | If accept is chosen as the response, generally the pre- and post-response assessment ratings remain the same.
Share | Allocates a portion of ownership of a risk threat to another party who is best able to minimize the impact and/or probability of the risks. Allocates all or a portion of ownership of a risk opportunity to another party who is best able to maximize its probability of occurrence and increase the potential benefits if it does occur. MnDOT and 3rd party share the benefits of the opportunity.
Threat Response
Mitigate | Seeks to reduce the probability and/or impact of a risks threat to below an acceptable threshold. | If mitigate is chosen as the response, generally the post response assessment is lower than the pre-response assessment.
Transfer | Allocates all ownership of a risk threat to another party who is best able to minimize the impact and/or probability of the risk. | If transfer is chosen as the response, generally the post response assessment is lower than the pre-response assessment. If the risk is fully transferred with no residual risk to MnDOT, the post-response assessment would equal zero. However, it is important to think about the cost of transferring the risk, which can be captured in the "Response Cost" column.
Avoid | Involves changing the project plan to eliminate the risk threat or to protect the project objectives from its impact. | If avoid is chosen as the response, generally the risk is totally eliminated in the post response assessment.
Opportunity Response
Enhance | Seeks to modify the “size” of a risk opportunity by increasing its probability and/or impact thereby maximizing benefits realized for the project.
Exploit | Seeks to eliminate the uncertainty associated with a particular upside risk by making the risk opportunity definitely happen - can be considered a more rigorous response than "enhance".
Urgency: | Rating of "High", "Medium", or "Low" in regards to when the risk needs to be addressed.
Project Impact (post-response): | Impacts to project objectives of quality, cost, and time. The post-response rating is the residual risk assuming the response plan has been implemented properly. See "Opportunity - Rating Desc." and "Threat - Rating Desc." tabs for general rating definitions to be used as guidance; however this is also subject to judgment of the project team. | These cells come prepopulated with values from the pre-response to assist with data entry in the post-response evaluation. The prepopulated values (formulas) should be overwritten with new ratings of 1 through 5 taking into account the response plan. If the response is to accept, the values would remain the same as the pre-response.
Severity (P): | The product of the probability and the highest rated project risk impact
Agency Impact (post-response): | Impacts to MnDOT's goals of safety, connectivity, congestion, and best-in-class agency (reputation, public perception, etc...). The post-response rating is the residual risk assuming the response plan has been implemented properly. See "Opportunity - Rating Desc." and "Threat - Rating Desc." tabs for general rating definitions to be used as guidance; however this is also subject to judgment of the project team. | These cells come prepopulated with values from the pre-response to assist with data entry in the post-response evaluation. The prepopulated values (formulas) should be overwritten with new ratings of 1 through 5 taking into account the response plan. If the response is to accept, the values would remain the same as the pre-response.
Severity (A): | The product of the probability and the highest rated agency risk impact
Severity (max): | The absolute value of the highest rated project and agency risk severity value - used primarily for sorting and normally hidden in reporting.
Priority | Priorities are either "high", "medium", or "low". - High priorities are generally items that require immediate action or discussions at a higher level than the project team. - Medium priorities are generally items that are being actively addressed or monitored by the proiect team. - Low priorities are identified items that are not being actively addressed or monitored, but are desired by the project team to remain on the register in the event that conditions change on the project.
Response: | Primary plan to address the risk. | Response plans should be specific enough to implement. It is okay to include steps to implementation. For example further study may be needed prior to implementing a response plan to determine whether it would be effective; or options may need to be evaluated and decided upon by the project team prior to implementation. Owners assigned are those who are best able to monitor the risk and implement the response. More than one owner can be assigned, but it should be clear what each owner is responsible for.
Risk Owner: | Person or people assigned to implement the response plan and monitor the risk. | If multiple people are assigned as owners, it should be clear what each of their roles are and what they are individually responsible for.
Trigger(s): | Description of events that may serve as indicators that a risk has occurred or is about to occur. Triggers help in monitoring the risk. Identification of triggers is recommended, but may not be applicable in all cases. | Think about potential risk triggers and list them if they apply. Triggers are not absolutely necessary for all risks, but are useful in monitoring. They are indications that the risk is about to occur or has occurred.
Contingency Plan: | For risks, this is the plan to address if the risk threat were to occur. Contingency plans allow for agreement of the plan in advance so that the plan can be implemented more efficiently in order to reduce impacts. Developing contingency plans is recommended, but may not be applicable in all cases. | Determine whether a contingency plan would be beneficial. Not all risks need a contingency plan but they are helpful for when a risk event does occur or the primary plan fails so there is a rough plan in place to put into action.
Response Cost: | Cost of the response plan as provided in the risk register for cost estimating purposes. This cost may be shown as negligible if it is reasonable to assume the costs can be absorbed into other project activities. Estimating response cost is recommended, but may not be applicable in all cases.
Agency Risk (X): | Automated box that includes an "X" for risks that are identified with Agency impacts.
Cost Impacts (X): | Automated box that includes an "X" for risks that are identified with cost impacts. | If performing the quantitative assessment, this box is an indicator that cost impacts (in millions of dollars) should be entered in cells AS through AU.
Schedule Impacts (X): | Automated box that includes an "X" for risks/issue that are identified with schedule impacts. | If performing the quantitative assessment, this box is an indicator that schedule impacts (in months) should be entered in cells AV through AX.
Maximum (Schedule) | The estimated maximum schedule impact of the risk if it were to occur (in months). For the initial risk assessment, this value should generally correlate with the pre-response assessment. For subsequent risk assessments as response plans are implemented, the value should reflect the estimated impact at the time of assessment.
Cost Impact | The adjusted cost impacts of the risk (in millions of dollars) taking into account the probability and the minimum, most likely, and maximum cost impacts. | The equation used is the product of the probability and weighted average of the minimum, most likely, and maximum values. (probability (%) * (minimum + 4*most likely + maximum)/6))
Schedule Impact | The adjusted schedule impacts of the risk (in weeks) taking into account the probability and the minimum, most likely, and maximum cost impacts. | The equation used is the product of the probability and weighted average of the minimum, most likely, and maximum values. (probability (%) * (minimum + 4*most likely + maximum)/6))
Status:
Active (Not Started) | Risk is being actively monitored and controlled, but the response plan has not been initiated.
Active (Ongoing) | Risk is being actively monitored and controlled, and the response plan is currently being implemented.
Active (Complete) | The risk is still being being actively monitored and controlled; however all work on the response plan is complete.
Dormant (Not Started) | Risk is not currently a high priority, but may become active in the future | This status is not often used.
Retired (Complete) | Risk is no longer a threat to project objectives | Risks that are no longer applicable should be listed as "retired" and not deleted from the register.
Tracking Comments: | Include any comments associated with the risk and the update to the risk in this box. | Utilize the comments section to provide updates on actions or owners, or to note changes associated with the response plans.

## Opportunity - Rating Desc.
Impact Rating
Context | Project Impacts
| -1 | -2 | -3 | -4 | -5
| Low | Medium-Low | Medium | Medium-High | High
Quality | Negligible improvements to design quality Negligible improvements to long-term maintenance Barely noticeable | Noticeable improvements to design quality Minor improvements to long-term maintenance Minor scope improvements | Significant improvements to design quality Significant improvements to long-term maintenance Significant scope improvements | Major improvements to design quality Major improvements to long-term maintenance Major scope improvements | Exceptional improvements to design quality Exceptional improvements to long-term maintenance Exceptional scope improvements
Cost (% of project cost) | cost savings = 1% | cost savings = 2% | cost savings = 3% | cost savings = 4% | cost savings > 5%
Schedule (% of project schedule, subject to schedule analysis) | schedule savings = 1% | schedule savings = 2% | schedule savings = 3% | schedule savings = 4% | schedule savings > 5%
Context | Agency Impacts
| -1 | -2 | -3 | -4 | -5
| Low | Medium-Low | Medium | Medium-High | High
Safety | Negligible safety improvements | Minor safety improvements | Significant safety improvements | Major safety improvements | Exceptional safety improvements
Congestion | Negligible congestion relief or additional capacity from anticipated scope within corridor | Noticeable congestion relief or additional capacity from anticipated scope within corridor | Significant congestion relief or additional capacity from anticipated scope at several points within the corridor or major congestion relief at single point within the corridor | Major congestion relief or additional capacity from anticipated scope at several points along the corridor or exceptional congestion relief at single point within the corridor | Exceptional congestion relief or additional capacity from anticipated scope at several points within the corridor
Connectivity | Negligible improvement from anticipated scope to project limits; or to throughput or connectivity at intersections, interchanges, or parallel or connecting roadways | Minor improvement from anticipated scope to project limits; or to throughput or connectivity at intersections, interchanges, or parallel or connecting roadways | Significant improvement from anticipated scope to project limits; or to throughput or connectivity at intersections, interchanges, or parallel or connecting roadways | Major improvement from anticipated scope to project limits; or to throughput or connectivity at intersections, interchanges, or parallel or connecting roadways | Exceptional improvements from anticipated scope to project limits; or to throughput or connectivity at intersections, interchanges, or parallel or connecting roadways
Best-in-class agency | Negligible benefit to agency's reputation | Minor benefit to agency's reputation, single press release | Significant benefit to agency's reputation, multiple press releases in regional news | Major benefit to agency's reputation, major industry awards, multiple press releases, statewide news | Exceptional industry recognition, multiple press releases, national news
Probability Rating
| 1 | 2 | 3 | 4 | 5
| Low | Medium-Low | Medium | Medium-High | High
Probability of occurrence | 1-15% | 16-30% | 31-65% | 66-80% | 81-99%
Note: probability scale for threats and opportunities are color coded the same to ensure conditional formatting of cells is consistent and severity rankings are calculated correctly
| 1 | 2 | 3 | 4 | 5
| Low | Medium-Low | Medium | Medium-High | High | Total | Needed to reach 100
Scale modifier | 15 | 15 | 35 | 15 | 20 | 100 | 0

## Threat - Rating Desc.
Impact Rating
Context | Project Impacts
| 1 | 2 | 3 | 4 | 5
| Low | Medium-Low | Medium | Medium-High | High
Quality | Negligible impacts to design quality Negligible impacts to long-term maintenance Barely noticeable | Requires Design Variance Minor impacts to long-term maintenance Minor scope reduction | Requires Design waiver Significant impacts to long-term maintenance Major scope reduction | Does not meet acceptable standards and requires Design Exception Major impacts to long-term maintenance Changes unacceptable to TxDOT or stakeholders | Does not meet acceptable standards and Design Exception not likely Unacceptable impacts to long-term maintenance Project does not meet need and purpose
Cost (% of project cost) | cost increase = 1% | cost increase = 2% | cost increase = 3% | cost increase = 4% | cost increase > 5%
Schedule (% of project schedule, subject to schedule analysis) | delay = 1% | delay = 2% | delay = 3% | delay = 4% | delay > 5%
Context | Agency Impacts
| 1 | 2 | 3 | 4 | 5
| Low | Medium-Low | Medium | Medium-High | High
Safety | First Aid | Restricted Duty / Doctor Visit | Recordable | Lost Time | Major injury or death
Congestion | Minor additional congestion or reduction in capacity from anticipated scope | Noticeable additional congestion or reduction in capacity from anticipated scope | Significant additional congestion or reduction in capacity from anticipated scope at several points or major congestion at single point within the corridor | Major additional congestion or reduction in capacity from anticipated scope at several points along the corridor or exceptional congestion at single point within the corridor | Unacceptable additional congestion or reduction in capacity from anticipated scope at any point within the corridor
Connectivity | Negligible decrease from anticipated scope to project limits; or to throughput or connectivity at intersections, interchanges, or parallel or connecting roadways | Minor decrease from anticipated scope to project limits; or to throughput or connectivity at intersections, interchanges, or parallel or connecting roadways | Significant decrease from anticipated scope to project limits; or to throughput or connectivity at intersections, interchanges, or parallel or connecting roadways | Major decrease from anticipated scope to project limits; or to throughput or connectivity at intersections, interchanges, or parallel or connecting roadways | Unacceptable decrease from anticipated scope to project limits; or to throughput or connectivity at intersections, interchanges, or parallel or connecting roadways
Best-in-class agency | Negligible impact to agency's reputation | Noticeable impact to agency's reputation, single press release | Significant impact to agency's reputation, multiple press releases in regional news | Major impact to agency's reputation, multiple press releases, statewide news | Potential legal action, multiple press releases, national news
Probability Rating
| 1 | 2 | 3 | 4 | 5
| Low | Medium-Low | Medium | Medium-High | High
Probability of occurrence | 1-15% | 16-30% | 31-65% | 66-80% | 81-100%
Note: probability scale for threats and opportunities are color coded the same to ensure conditional formatting of cells is consistent and severity rankings are calculated correctly
| 1 | 2 | 3 | 4 | 5
| Low | Medium-Low | Medium | Medium-High | High | Total | Needed to reach 100
Scale modifier | 15 | 15 | 35 | 15 | 20 | 100 | 0

## Severity matrix
|  | Low | Med- Low | Med | Med- High | High
Probability | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
Consequence
Probability | 5 | -5 | -10 | -15 | -20 | -25
| 4 | -4 | -8 | -12 | -16 | -20
| 3 | -3 | -6 | -9 | -12 | -15
| 2 | -2 | -4 | -6 | -8 | -10
| 1 | -1 | -2 | -3 | -4 | -5
|  | 1 | 2 | 3 | 4 | 5
Consequence

## Sample Risk Checklist
Context | Risk Description
Cost | ROW acquisition costs higher than anticipated
Cost | Unexpected geotechnical or groundwater issues
Cost | Contingency comsumption above anticipated based on planned risk distribution/sharing
Cost | Unanticipated escalation in righto fo way values or construction cost
Cost | Unplanned work that must be accommodated
Cost | Estimating and/or scheduling errors
Cost | Force Majeure Events such as natural catastropes, sabotage and terrorism
Cost | Developer usese non-standard components in maintenance replacements not in line with Department then-current techincal requirements or standards, e.g. different tolling or ITS components
Environmental | Design changes require additional Environmental analysis
Environmental | Environmental regulations change
Environmental | MPO model changes due to conformity
Environmental | Air quality attainment impacts travel demand
Environmental | Hazardous waste site analysis incomplete
Environmental | NEPA compliance 150d lawsuit window - will we get sued?
Financial | Lack of understanding of complex internal funding procedures
Financial | Funding changes for fiscal year
Financial | Capital funding unavailable for right of way or construction
Financial | Global market conditions
Financial | Potential inadequate local access to materials, labor, resources
Financial | Labor shortage or strike
Financial | Contract execution may need revisions to financial terms in the agreement
Financial | Financial failure of Developer during construction or full term
Financial | Bond availability & favorable terms secured
Financial | Developer not financially closing
Legal | Unforeseen agreements required
Legal | External agreement development
Legal | Unable to meet Americans with Disabilities Act requirements
Legal | Developer contract legal sufficiency determination
Legal | Terms of toll service agreement
Legal | Added workload or time requirements because of new direction, policy, or statute
Legal | Dispute on terms of agreement or technical provisions during construction
Operational | Losing critical staff at crucial point of the project
Operational | Functional units not available, overloaded
Operational | Internal “red tape” causes delay getting approvals, decisions
Operational | Inexperienced staff assigned
Operational | Lack of specialized staff (biology, anthropology, geotechnical, archeology, etc.)
Operational | Readiness to prepare, review, & deliver ROW acquisition packages
Operational | Operational concerns relative to timing of support staff
Operational | Readiness & ability to review & approve design deliverables
Operational | Railroad involvement causes delays or additional scope/cost
Operational | No control over staff priorities
Operational | Goals & needs to aid the project may counter District or higher level goals & needs, e.g. good relationships with locals
Operational | Communication/Coordination failure between state, project, developer, public, MPOs, etc.
Operational | Unanticipated project manager workload
Operational | Data management system malfunction
Political / Public | Local agency support not attained
Political / Public | Priorities change on existing program
Political / Public | New stakeholders emerge and request changes
Political / Public | Reviewing agency requires longer than expected review time
Political / Public | Public perception during construction, e.g. lane closures, business disruption
Political / Public | Public Perception of Value of (interim) facility being constructed
Political / Public | Successful Attainment of DBE Compliance by Developer
Political / Public | Landowners unwilling to sell
Political / Public | Controversy on environmental grounds causing project delay or re-evaluation
Political / Public | Stakeholders request late changes
Political / Public | Political factors or support for project changes
Political / Public | Unreasonably high expectations from stakeholders
Political / Public | Construction or pile driving noise and vibration impacting adjacent businesses or residents
Political / Public | Anti-toll groups challenge NEPA decision
Political / Public | Legislative support for TxDOT and SPD - political position viable?
Political / Public | Highly involved local leadership preferences for project in control of developer
Political / Public | Public acceptance of tolling roads
Political / Public | Additional congestion in proximity to corridor during construction
Quality / Performance / Scope | Inconsistent cost, time, scope and quality objectives
Quality / Performance / Scope | Overlapping of one or more project limits, scope of work or schedule
Quality / Performance / Scope | Construction quality sufficient to meet short- and long-term maintenance expectations
Quality / Performance / Scope | Construction quality sufficient to meet specifications and expectations for aesthetics and safety
Quality / Performance / Scope | Unforeseen design exceptions required
Quality / Performance / Scope | Unresolved constructability items
Quality / Performance / Scope | Inaccurate assumptions on technical issues in planning stage
Quality / Performance / Scope | Scope creep
Quality / Performance / Scope | Unresolved project conflicts not escalated in a timely manner
Quality / Performance / Scope | Change requests due to differing site conditions
Quality / Performance / Scope | Project purpose and need is not well-defined
Quality / Performance / Scope | Project scope definition is incomplete
Quality / Performance / Scope | Project scope, schedule, objectives, cost, and deliverables are not clearly defined or understood
Quality / Performance / Scope | Department-directed changes required during detailed design stage due to Department preference, political or public pressure or other external influences
Quality / Performance / Scope | Unexpected 3rd party requirements during construction
Quality / Performance / Scope | Capacity improvements not built within timeframes originally predicted or not built to suit reasonable travel demand so resulting in deteriorating level of service, not meeting stakeholder expectations, and/or not meeting environmental commitments.
Schedule | Permits delayed or take longer than expected
Schedule | ROW acquisition progressing slower than anticipated
Schedule | Consultant or contractor delays
Schedule | Utility relocation requires more time than planned
Schedule | Delay in earlier project phases jeopardizes ability to meet programmed delivery commitment
Schedule | Underestimated support resources or overly optimistic delivery schedule

## Lists
Categories | [14 empty] | Status
PM | Organizational | Environmental | Design | ROW | Railroad | Utilities | External | Construction | Maint_Ops | [5 empty] | Identified | – Risk documented, but analysis not performed
Estimating | Project Dependencies | Requirements | Structures | Requirements | Requirements | Requirements | Contractor | Site/ Environmental Conditions | Pavement | [5 empty] | Analysis Complete | – Risk analysis done, but response planning not performed
Planning/ Scope | Resources | Documentation | Drainage | Coordination | Coordination | Coordination | Subcontractors/ Suppliers | Requirements | Structures | [5 empty] | Planning Complete | – Response planning complete
Controlling | Funding/ Financing | Coordination | Traffic Control | Design | Design | Design | Political Stakeholders | Materials | ITS | [5 empty] | Triggered | – Risk trigger has occurred and threat has been realized
Communications | Prioritization |  | Geotechnical | Funding / Cost |  |  | Public Stakeholders | Traffic Control | Tolling | [5 empty] | Resolved | – Realized risk has been contained
Schedule | Policy |  | Survey |  |  |  | Other Agencies | Phasing | Drainage | [5 empty] | Retired | – Identified risk no longer requires active monitoring (e.g. risk trigger has passed)
|  |  | Roadway |  |  |  | Legislative/ Legal | Performance/ Reliability | Routine Maintenance
|  |  | Grading |  |  |  | Market Conditions | Complexity and Interface | Other
|  |  | Aesthetics |  |  |  | Competition
Signing/ Lighting/ Signals
ITS
Bike Pedestrian
Tolling
Column B | Column E | Column V |  | Column F |  | Column W | Column D
Risk Type | Risk Type | Response Category | Urgency | Risk/Issue | Status |  | Planning/Scoping
Project | Opportunity | Avoid | High | Risk | Not Started | Yes | Design
Program | Threat | Transfer | Medium |  | Active (Ongoing) | No | ROW-Utilities
| Both | Mitigate | Low |  | Dormant (Not Started) |  | Construction
|  | Share |  |  | Retired (Complete) |  | Maintenance
Accept
Exploit
Enhance
Project Phases (note, some will be in both camps) | Planning/ Preliminary Engineering |  |  |  | Program/ Procurement | [5 empty] | Design & Construction |  |  | Operations & Maintenance
WBS Tier 1 (Risk Category) Note some will cross phases | Environmental | Design | R/W-Utilities-RR | Traffic | Hydraulics | Organizational | Bridge | Public | Cultural Resources | Funding | Geotechnical/Materials | Design | Construction | Regulatory
Examples | NEPA documents | Survey |  |  | Staffing |  |  | Other agencies |  |  |  | Permitting | Work windows
| Environmental permitting | Roadway | [9 empty] | Traffic control & phasing | Traffic control & phasing
| Haz. Mat. | Grading
| Stormwater | Aesthetics
Noise mitigation
| Archaeological/ cultural | Signing/ Lighting/ Signals
Bike Pedestrian
Tolling
ITS
Structures
Drainage
Traffic Control
Exploit
Enhance

## Instructions
INSTRUCTIONS ON HOW TO COPY THIS TEMPLATE
PLEASE NAVIGATE TO FILE THEN CLICK ON MAKE A COPY (SEE ATTACHED IMAGE BELOW)