## Risk Register
[Insert Department/Project Logo] | [15 empty] | [Insert Department Name] [Insert Project Name]
Risk Register
Risk Identification | [5 empty] | Risk Analysis |  |  |  | Risk Prioritization |  |  | Risk Response |  |  | Risk Control
ID # | Risk Title | Risk Statement or Description | Date Risk Identified | Risk Originator | Risk Category | Probability | Impact | Timeframe | Exposure | Severity | Risk Owner | Date Assigned | Risk Response Strategy | Risk Response Plan Description | Contingency Plan Description | Risk Status | Risk Resolution | Risk Closure Date
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0

## Instructions
INSTRUCTIONS ON HOW TO COPY THIS TEMPLATE
PLEASE NAVIGATE TO FILE THEN CLICK ON MAKE A COPY (SEE ATTACHED IMAGE BELOW)

## Introduction
[Insert Department/Project Logo] |  | [Insert Department Name] [Insert Project Name]
Introduction to the Risk Register Template
Risk management can be defined as the processes and structures that are directed towards realizing potential opportunities, while simultaneously managing possible adverse impacts. From a project management perspective, risk management is a continuous activity conducted throughout the life of the project. It seeks to identify potential risks, evaluate their likely impact, develop mitigation plans, and monitor progress.
The following sections are constructed to match the suggested heading structure for the Risk Register Template. Each section provides instructions and descriptions to guide the reader into understanding the section purpose and how to complete it.
Template style conventions are as follows:
Style | Convention
Normal text | Indicates placeholder text that can be used for any project
[Instructional text in brackets] | [Indicates text that is to be replaced/edited/deleted by document author]
Example text in italics | Indicates example text that might be replaced/edited/deleted by user

## Guide
[Insert Department/Project Logo] |  |  |  | [Insert Department Name] [Insert Project Name]
Risk Register Template
1 Introduction
[The Risk Register is a tool to capture project risks and supports the Risk Management processes the Project Manager uses throughout the project. The Risk Register supports the five Risk Management processes listed as follows:
• Risk Identification
• Risk Analysis
• Risk Prioritization
• Risk Response
• Risk Control
The following sections describe the attributes used in each of the five sections listed above and provide instruction and guidance for how to fill in the Risk Register tool. See the Risk Management Plan for additional information about the Risk Management processes.]
2 Risk Identification
[The Risk Identification section of the Risk Register consists of the following attributes. Attribute descriptions are provided to help understand usage.]
• ID # - A unique identifier used to reference the risk.
• Risk Title – The title appears on risk reports. It should be brief but also convey the risk threat or opportunity.
• Risk Statement or Description – The description should contain detail sufficient to assess risk impact and provide project Stakeholders with an understanding of risk to the project. Risk Statement = Concern + Likelihood + Consequence.
• Date Risk Identified – Enter the date the risk was added to the Risk Register.
• Risk Originator – Enter the person(s) who identified the risk.
• Risk Category – List the risk category. Categorizing risks provides a grouping mechanism to help identify potential source or causes of risks. This is a drop-down list containing, but not limited to, the following selections: Budget, Environment, Processes, Resources, Schedule, Stakeholders, and Technology.
Example:
Risk Identification
ID # | Risk Title | Risk Statement or Description | Date Risk Identified | Risk Originator | Risk Category
1 | Competing Team Member Priorities | Team Members are not fully dedicated to the project and have multiple competing assignments. | 2016-02-01 | Project Manager | Resources
2 | Current costs are outpacing budget | The current project costs are ahead of the planned cost for this period in the project. | 2016-03-15 | Project Sponsor | Budget
3 | Schedule is Aggressive and High Risk | The current project schedule baseline is aggressive and considered high risk for completing project work on time. | 2016-04-01 | Technical Manager | Schedule
3 Risk Analysis
[The Risk Analysis section of the Risk Register consists of the following attributes. Attribute descriptions are provided to help understand usage.
• Probability - Probability is a quantitative or qualitative expression of the chances or odds a risk will occur. The value is used in calculating risk exposure level.
High – Very likely or almost certain (66% – 99%) risk will occur
Medium – A likely chance (34% – 65%) risk will occur
Low – Unlikely or will probably not (1% – 33%) occur
• Impact – This element is used to describe the impact to the project should the risk occur. The value is used in calculating risk exposure level.
High – The Risk presents a significant negative impact on project budget, schedule, or quality. - Project cost increase of 11% or more - Project schedule increase of 11% or more - Failure to meet required performance - Failure to provide required functionality
Medium – The Risk presents a material impact that would moderately affect users, clients, or key Stakeholders. - Project cost increase between 5% and 10% - Project schedule increase between 5% and 10% - Moderate discrepancies in desired system-wide performance - Moderate discrepancies in desired system-wide functionality
Low – The Risk does not present a significant or material impact on project budget, schedule, or quality. - Project cost increase of less than 5% - Project schedule increase of less than 5% - Minor discrepancies in desired performance - Minor discrepancies in desired functionality
• Timeframe – This element indicates when a risk response must be performed in order to be effective. The value is used in calculating severity. It indicates how quickly action must be taken on the risk. For example (timeframes are examples only and can be decided by the Project Sponsor):
High – Risk Management action required within [two weeks]
Medium – Risk Management action required within [30 days]
Low – Risk Management action required within [90 days]
• Exposure – This is a calculated field. Exposure level = Probability multiplied by Impact. Risk level is reviewed by the Risk Manager on a periodic basis based on input from the Risk Owner.
High = 3
Medium = 2
Low = 1
Example:
Risk Identification | [5 empty] | Risk Analysis
ID # | Risk Title | Risk Statement or Description | Date Risk Identified | Risk Originator | Risk Category | Probability | Impact | Timeframe | Exposure
1 | Competing Team Member Priorities | Team Members are not fully dedicated to the project and have multiple competing assignments. | 2016-02-01 | Project Manager | Resources | High | High | Medium | 9
2 | Current costs are outpacing budget | The current project costs are ahead of the planned cost for this period in the project. | 2016-03-15 | Project Sponsor | Budget | Medium | Medium | Short | 4
3 | Schedule is Aggressive and High Risk | The current project schedule baseline is aggressive and considered high risk for completing project work on time. | 2016-04-01 | Technical Manager | Schedule | Medium | High | Short | 6
4 Risk Prioritization
[The Risk Prioritization section of the Risk Register consists of the following attributes. Attribute descriptions are provided to help understand usage.]
• Severity - This is a calculated field. Severity level = Risk Exposure multiplied by Time Frame. The severity level is reviewed by the Risk Manager on a biweekly basis based on input from the Risk Owner.
• Risk Owner – The Risk Owner is responsible for managing assigned risks, including monitoring and development of mitigation strategies and contingency plans.
• Date Assigned – Reflects the date the Risk Owner was identified and assigned to the risk.
Example:
Risk Identification | [5 empty] | Risk Prioritization
ID # | Risk Title | Risk Statement or Description | Date Risk Identified | Risk Originator | Risk Category | Severity | Risk Owner | Date Assigned
1 | Competing Team Member Priorities | Team Members are not fully dedicated to the project and have multiple competing assignments. | 2016-02-01 | Project Manager | Resources | 18 | Project Manager | 2016-02-08
2 | Current costs are outpacing budget | The current project costs are ahead of the planned cost for this period in the project. | 2016-03-15 | Project Sponsor | Budget | 4 | Project Sponsor | 2016-03-22
3 | Schedule is Aggressive and High Risk | The current project schedule baseline is aggressive and considered high risk for completing project work on time. | 2016-04-01 | Technical Manager | Schedule | 6 | Project Manager | 2016-04-08
5 Risk Response
[The Risk Response section of the Risk Register consists of the following attributes. Attribute descriptions are provided to help understand usage.]
• Risk Response Strategy - Identifies a strategy for attempting to reduce negative impacts of risk occurrence or increase the potential for an opportunity. The project risk management team jointly determines the risk response strategy for each risk. This is a drop-down list including, but not limited to, Accept, Avoid / Exploit, Mitigate / Enhance, and Watch.
• Risk Response Plan Description – Details the risk response plan to address the risk. Used to reduce probability of negative impacts of risk occurrence, or increase potential for an opportunity. This represents a set of actions and requires resource and timing considerations.
• Contingency Plan Description – Describes procedures to follow if a risk occurs. This represents an alternate set of actions and requires resource and timing considerations. The contingency plan is integrated into the project plan and evaluated for additional risks and impacts.
Example:
Risk Identification |  |  | Risk Response
ID # | Risk Title | Risk Statement or Description | Risk Response Strategy | Risk Response Plan Description |  | Contingency Plan Description
1 | Competing Team Member Priorities | Team Members are not fully dedicated to the project and have multiple competing assignments. | Transfer / Share | Meet with team member organizational managers and set this project as highest priority. |  | Escalate to Executive Steering Committee for analysis and resolution.
2 | Current costs are outpacing budget | The current project costs are ahead of the planned cost for this period in the project. | Mitigate / Enhance | Monitor actual costs on a bi-weekly basis. Work with financial manager on mitigation strategies. |  | Implement cost reduction strategies within 30 days.
3 | Schedule is Aggressive and High Risk | The current project schedule baseline is aggressive and considered high risk for completing project work on time. | Watch | Carefully monitor work performance and search for opportunities to reduce risk. |  | Re-work and re-baseline the schedule to be less aggressive.
6 Risk Control
[Risk Control is the process of implementing risk response plans, tracking identified risks, monitoring residual risks, identifying new risks, and evaluating risk process effectiveness throughout the project.]

## Data (hidden)
Low | Budget | Accept | Open
Medium | Environment | Avoid/Exploit | Closed
High | Processes | Mitigate/Enhance
| Resources | Transfer/Share
Short | Schedule | Watch
Medium | Stakeholders
Long | Technology