## Risk Register
Project name
Date updated
Risk ID | Risk Title | Description / Cause / Consequence | Risk Owner | Status | Date Raised | Threat / Opportunity | Established Control(s) | Pre-Treatment |  |  |  | Post-treatment |  |  | Residual controls | Modelling notes
[8 empty] | Likelyhood | Consequence | Risk rating | Treatment plan summary | Probability | Impact | Risk rating
Example 1 | Poor ground condition | Testing indicates the current identified site has liquefiable and reactive soils. |  | Open |  |  |  | Likely | Major | Extreme Threat | Reduce - Early works package to excavate majority site and fill with cement stabilised earth. Further detail provided in treatment plan #001 | Unlikely | Medium | Moderate Threat | Transfer - Once site remediation complete, include in main works contract the requirement for the contractor to accept the site condition | Best case = $0.5M and 4 weeks delay, Worst Case = $1.25M and 8 weeks delay. Use normal distribution to model

## Variables
T/O | Consequence | Likelihood | Risk Rating | Risk Status | Risk / Value
Threat | Very Low | Rare | Low Threat | Open | Risk
Opportunity | Minor | Unlikely | Moderate Threat | Closed | Value
| Medium | Possible | High Threat
| Major | Likely | Extreme Threat
| Substantial | Almost Certain | Low Opportunity
Moderate Opportunity
High Opportunity
Substantial Opportunity

## Instructions
INSTRUCTIONS ON HOW TO COPY THIS TEMPLATE
PLEASE NAVIGATE TO FILE THEN CLICK ON MAKE A COPY (SEE ATTACHED IMAGE BELOW)