## Dvlpmt & Pro Risk Register
Risk Register
[Procurement Approach]
Project: |  | [Name]
Project Manager: |  | [Name]
Development Stage: |  | [Decision Point]
Risk Information |  |  |  |  | Risk Analysis | [22 empty] | Response |  |  | Risk Tracking | [5 empty] | Notes
Risk Number (1) | Risk Category (2) | Risk Topic (3) | Impact Phase (4) | Risk Description (5) | Consequence of Risk (6) | RAG Analysis | [10 empty] | Expected Value Analysis | [8 empty] | Monte Carlo Simulation (10c) |  | Risk Response Method (12) | Risk Allocation (13) | Risk Allocation Notes (14) | Monitoring and Control (14) | [5 empty] | Risk Closure Notes (15) | Lessons Learned/Contract Notes (16)
[6 empty] | Probability Range (7) | Cost Impact (8a) |  |  |  |  | Schedule Impact (8b) |  |  |  |  | Probability (9) | Cost Impact (10a) |  |  |  | Schedule Impact (10b) | [8 empty] | Risk Owner | Response Action/ Strategy to Mitigate Risk | Planned Mitigation Cost ($) | Risk Review Dates | Status and Review Comments | Is Risk on Critical Path?
[7 empty] | Consequence | Probability Rank | Consequence Rank | Impact Rank | Risk Impact | Consequence | Probability Rank | Consequence Rank | Impact Rank | Risk Impact |  | Min ($000) | Most Likely ($000) | Max ($000) | Risk Value ($000) | Min (Mos.) | Most Likely (Mos.) | Max (Mos.) | Risk Value (Mos.) | Distribution Type | Modeling Notes
1.01 | Planning and Approvals | Procurement Process | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
1.02 | Planning and Approvals | Permitting | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
1.03 | Planning and Approvals | NEPA Approvals | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
1.04 | Planning and Approvals | NEPA Approvals | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
1.05 | Planning and Approvals | Design Approvals | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
1.06 | Planning and Approvals | Design Approvals | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
1.07 | Planning and Approvals | Historic / Cultural Resources | Construction |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
2.01 | Legislative / Policy | Legislative Change | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
2.02 | Legislative / Policy | Regional / Local Support | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
2.03 | Legislative / Policy | Political / Policy Change | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
2.04 | Legislative / Policy | Legal Challenge | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
3.01 | Commercial / Procurement | Market Interest | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
3.02 | Commercial / Procurement | Bonding | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
3.03 | Commercial / Procurement | Insurance | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
3.04 | Commercial / Procurement | Contract Failure / Dispute | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
3.05 | Commercial / Procurement | Construction Inflation | Construction |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
3.06 | Commercial / Procurement | Adverse Weather Conditions | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
4.01 | Funding/ Finance | Cost / Availability of Finance | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
4.02 | Funding/ Finance | Financing | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
4.03 | Funding/ Finance | Public Funding | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
4.04 | Funding/ Finance | Financial Model | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
5.01 | Environmental | Hazmat Discovered | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
5.02 | Environmental | Hazmat Introduced | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
5.03 | Environmental | Endangered Species | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
6.01 | ROW/ Utilities | Unknown Utilities | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
6.02 | ROW/ Utilities | Uncooperative Utility Companies | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
6.03 | ROW/ Utilities | ROW Acquisition | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
6.04 | ROW/ Utilities | ROW Acquisition | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
6.05 | ROW/ Utilities | ROW Acquisition | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
7.01 | Design | Design Criteria / Technical Provisions | Development |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
7.02 | Design | Project Scope | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
7.03 | Design | Project Requirements | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
7.04 | Design | Reference Information Data | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
7.05 | Design | NS Railroad Crossing | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
7.06 | Design | Frontage Roads | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
7.07 | Design | Security | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
7.08 | Design | Drainage | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  | 0
Risk Allocation Options
Agency
Contractor
Concessionaire
Shared

## Imp & Ops Risk Register
Risk Register
[Procurement Approach]
Project: |  | [Name]
Project Manager: |  | [Name]
Development Stage: |  | [Decision Point]
Risk Information |  |  |  |  | Risk Analysis | [23 empty] | Response |  |  | Risk Tracking | [5 empty] | Notes
Risk Number (1) | Risk Category (2) | Risk Topic (3) | Impact Phase (4) | Risk Description (5) | Consequence of Risk (6) | RAG Analysis | [10 empty] | Expected Value Analysis | [9 empty] | Monte Carlo Simulation (10c) |  | Risk Response Method (12) | Risk Allocation (13) | Risk Allocation Notes (14) | Monitoring and Control (14) | [5 empty] | Risk Closure Notes (15) | Lessons Learned/Contract Notes (16)
[6 empty] | Probability Range (7) | Cost Impact (8a) |  |  |  |  | Schedule Impact (8b) |  |  |  |  | Probability (9) | Frequency (9.1) | Cost Impact (10a) |  |  |  | Schedule Impact (10b) | [8 empty] | Risk Owner | Response Action/ Strategy to Mitigate Risk | Planned Mitigation Cost ($) | Risk Review Dates | Status and Review Comments | Is Risk on Critical Path?
[7 empty] | Consequence | Probability Rank | Consequence Rank | Impact Rank | Risk Impact | Consequence | Probability Rank | Consequence Rank | Impact Rank | Risk Impact |  |  | Min ($000) | Most Likely ($000) | Max ($000) | Risk Value ($000) | Min (Mos.) | Most Likely (Mos.) | Max (Mos.) | Risk Value (Mos.) | Distribution Type | Modeling Notes
1.01 | Implementation | Labor | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.02 | Implementation | DBE / SWAM Goals | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.03 | Implementation | QA/QC | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.04 | Implementation | Traffic Management | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.05 | Implementation | Environmental Compliance | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.06 | Implementation | Subsurface Conditions | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.07 | Implementation | VDOT Contract Administration | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.08 | Implementation | Existing Infrastucture | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.09 | Implementation | Materials Quality | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.1 | Implementation | Materials Supply | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.11 | Implementation | Constructability | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.12 | Implementation | Performance - Supply Chain | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.13 | Implementation | Contract Management | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
1.14 | Implementation | Testing & Commissioning | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
2.01 | Force Majeure | Hurricane, Earthquake, Terrorist Attack, War, Pandemic | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
2.02 | Force Majeure | Hurricane, Earthquake, Terrorist Attack, War, Pandemic | Implementation |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
3.01 | Legislative / Policy | Legislative Change | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
3.02 | Legislative / Policy | Public Information and Relations | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
4.01 | Commercial / Procurement | General Economic Conditions | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
4.02 | Commercial / Procurement | Cost / Availability of Finance | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
4.03 | Commercial / Procurement | Connecting Facilities | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
4.04 | Commercial / Procurement | Traffic and Revenue | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
4.05 | Commercial / Procurement | Traffic and Revenue | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
4.06 | Commercial / Procurement | Contract Failure / Dispute | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
4.07 | Commercial / Procurement | Competing Facilities | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
5.01 | Operations | Incident Management | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
5.02 | Operations | Toll Violations | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
5.03 | Operations | CSC / Back Office Operations Center | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
5.04 | Operations | Control Center | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
5.05 | Operations | Tolling Operations | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
5.06 | Operations | New Technology / Interoperability | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
5.07 | Operations | Operations Staffing | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
5.08 | Operations | Security | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
5.09 | Operations | Utilities | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
6.01 | Maintenance | Maintenance Standards | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
6.02 | Maintenance | Maintenance Standards | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
6.03 | Maintenance | Maintenance Standards | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
6.04 | Maintenance | Maintenance Performance | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
6.05 | Maintenance | Frontage Roads | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
6.06 | Maintenance | Routine Maintenance | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
6.07 | Maintenance | Drainage and Ponding | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
6.08 | Maintenance | Maintenance Staffing | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
7.01 | Capital Maintenance | Latent Defects | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
7.02 | Capital Maintenance | Latent Defects | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
7.03 | Capital Maintenance | Capital Maintenance Performance | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
7.04 | Capital Maintenance | Management of Traffic | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
7.05 | Capital Maintenance | Flooding | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
7.06 | Capital Maintenance | Handover/ Handback | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
8.01 | Force Majeure | Major Storm, Earthquake, Terrorist Attack, War, Pandemic | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0
8.02 | Force Majeure | Major Storm, Earthquake, Terrorist Attack, War, Pandemic | Operations |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | [6 empty] | 0 |  |  |  | 0

## Typical Risks - Highway Project
Risk Number (1) | Risk Category (2) | Risk Topic (3) | Impact Phase (4) | Risk Description (5) | Consequence of Risk (6)
| Planning and Approvals | Environmental Approval | Development | Delay in achieving Record of Decision (or equivalent) | Increased project cost due to inflation and mismatch between funding sources and uses.
| Planning and Approvals | Permits | Construction | Local, Regional, State and Federal permits and approvals are not approved | Delay while approvals are revised and resubmitted. Material changes in project scope to meet approval requirements could result in increase cost of re-design, construction and mitigations
| Legislative / Policy | Legislative / Regulatory Change | Development | Discriminatory change in legislation or regulations that affects the project scope or design before the contract is awarded | Delay while work-around is developed, may result in increase of budget to carry out additional works and meet new requirements.
| Legislative / Policy | Legislative / Regulatory Change | Construction | Discriminatory change in legislation or regulations that affects the works after the contract is awarded, e.g. increase in health and safety requirements | Delay while impact of change is evaluated. Increased cost of additional requirements.
| Legislative / Policy | Legal Challenge | Development | Litigation on the Environmental Documents attmpting to change, stop or delay the project | Successful injunction will halt the project leading to delay and cost of disruption. Delay while litigation is resolved. Project may be cancelled if suit is successful.
| Legislative / Policy | Ability to Toll [IF APPLICABLE] | Development | Agency is unable to get approval for tolling the facility | Project no longer feasible without additional funds from elsewhere.
| Legislative / Policy | Regional Plan | Development | Change in Six Year Improvement Plan or State Transportation Improvement Plan reduces priority placed on the project | Funding may be witheld or postponed, delay and cost of disruption. Project may be cancelled.
| Stakeholders | Project Support | Development | Loss of support for the project, stakeholders disagree on scope, decisions are not made in timely manner | Leads to delays while decisions take excessive amount of time to resolve. Development cost increase if changes are made to decisions previously agreed and developed further. Funding may be witheld or delayed.
| Stakeholders | Stakeholder Coordination | Construction | Stakeholders change their minds about scope of project and request additional works | Scope creep - delay while additional works are evaluated, design and constructed (if approved). Additional cost of new works.
| Stakeholders | Third Party Claims | Construction | Claims related to property damage due to construction activities | Cost and use of management time to resolve claims.
| Stakeholders | Complaints | Operations and Maintenance | Stakeholders complain about operations and maintenance activities | Disruption of services, evaluation of complaints, additional cost of outreach and changes to operations.
| Stakeholders | Resistence to Tolling [IF APPLICABLE] | Operations and Maintenance | Toll rates set too high for economic benefit | Reduced revenue
| Commecial / Procurement | Cost Estimates / Design Contingency | Development | Approximations are used for quantities and unit prices during early stages of design and Design Contingencies are applied, contingency insufficient to cover revised cost estimate prepared later on in the design process | Budget has to be increased, funding gap may appear, political pressure may be applied to change, delay or cancel the project.
| Commecial / Procurement | Construction Market Capacity | Development | Insufficient Construction market capacity to attract main contractors and subcontractors | Construction of other facilities or general economic conditions may restrict capacity of the industry to be able to build the facility in the timeframe expected - result in delay and escalation cost increase.
| Commecial / Procurement | Prolonged Procurement | Development | Choice of procurement method requires prolonged negotiations | Delay to achieving commercial close / contract award. May involve change in financial markets that increases cost of funds.
| Commecial / Procurement | Bid Protest | Development | Protest by unsuccessful bidder | Possible delay to award of contract if injunction is achieved, increase in project cost as a result of the delay (inflation and disruption).
| Commecial / Procurement | Construction Contract Dispute | Construction | Dispute arises between Agency and Contractor | Disruption related to increased burden on senior management within Agency and Contractor organizations.
| Commecial / Procurement | O&M Contract Dispute | Operations and Maintenance | Dispute arises between Agency and Contractor | Disruption related to increased burden on senior management within Agency and Contractor organizations.
| Commecial / Procurement | Market Interest | Development | Lack of interest in the project from the construction industry, limited number of biiders, bidders withdraw | Reduces competitive pressure on prices, may be forced into sole source negotiation which may not provide value for money.
| Commecial / Procurement | Traffic and Revenue [IF APPLICABLE] | Operations and Maintenance | Traffic is less than forecasted, ramp up is longer than forecasted | Reduced revenue
| Commecial / Procurement | Construction Inflation | Construction | Inflation is higher than expected | Increased costs in year of expenditure.
| Commecial / Procurement | Performance Guarantees | Development | Onerous performance guarantee / bonding requirements | Requirements are expensive for Proposers which increases bid prices.
| Commecial / Procurement | Construction Insurance | Construction | Onerous insurance requirements | Increased costs
| Commecial / Procurement | O&M Insurance | Operations and Maintenance | Onerous insurance requirements | Increased costs
| Commecial / Procurement | Competing Facilities [IF APPLICABLE] | Operations and Maintenance | Traffic diverts to alternative facilities | Reduced revenue
| Commecial / Procurement | Connecting facilities [IF APPLICABLE] | Operations and Maintenance | Delay to completion of connecting facilities that were assumed to exist in the traffic forecasts | Reduced revenue
| Commecial / Procurement | Sponsor / SPV Financial Difficulty / Default | Operations and Maintenance | Project revenues / payments are insufficient to repay debt and equity distributions resulting in SPV insolvency and step in by lenders / Agency | Increased costs
| Commecial / Procurement | Construction Contractor Financial Difficulty / Default | Construction | Contractor or subcontractors are unable to meet financial commitments on this project or across their business, bonding companies may be required to complete project | Contractor or subcontractor bankruptcy resulting in significant delay. Dealing with bonding company and lawyers would result in significant delays and additional costs.
| Commecial / Procurement | O&M Contractor Financial Difficulty / Default | Construction | Contractor or subcontractors are unable to meet financial commitments on this project or across their business | Contractor or subcontractor bankruptcy resulting in significant delay. Dealing with bonding company and lawyers would result in significant delays and additional costs.
| Commecial / Procurement | Taxation | Development | Change in taxation rules, responsibility to pay taxes | Increased costs
| Funding / Finance | Public Funding | Development | Public funding is withdrawn | Project delayed while new funding sources are located. Project may be cancelled.
| Funding / Finance | Timing of Funds | Development | Allocated funding is not available when needed | Project schedule has to be adjusted to accommodate revised timing of funds.
| Funding / Finance | Availability of Finance | Development | Limitations on bonding and / or debt capacity needed to finance the project, lenders object to risk level, availability of equity, bridge financing | May need to identify alternative sources of finance which may increase overall cost of the project. Delay while sources are evaluated.
| Funding / Finance | Interest Rates | Development | Availability of interest rate hedge | Increased cost of funds.
| Funding / Finance | Conditions Precedent | Development | Fulfillment of conditions precedent for debt disbursement | Delay while conditions are met.
| Funding / Finance | Financial Model | Development | Errors or omissions in base case financial model or assumptions | Prolonged negotiations, revision of terms, delays. May impact project feasibility.
| Environmental | Environmental Documents | Development | Environmental Documentation is incomplete | Approval may be delayed, additional cost and delay to project start.
| Environmental | Environmental Impacts / Mitigations | Construction | Mitigations insufficient to overcome environmental impacts | Mitigations identified in Environmental Documentation must be carried out. If other mitigations are required during construction this may cause delay and additional costs.
| Environmental | Environmental Impacts / Mitigations | Operations and Maintenance | Further residential, business and retail development along roadway requires construction of additional infrastructure, such as noise walls. | Environmental regulations change to expand noise management to all residential and commercial areas along the ROW or for new communities.
| Environmental | Environmental Incidents During Construction | Construction | Incident occurs during construction that has negative impact on the environment (pollution) | Clean up required - may cause delay to works and additional cost.
| Environmental | Environmental Incidents During Operations | Operations and Maintenance | Incident occurs during operations that has negative impact on the environment (hazmat / pollution) | Clean up required - may cause disruption to traffic, loss of revenue [IF TOLLED] and additional cost.
| Environmental | Historical Artifacts | Construction | Historical artifacts are uncovered during construction that were not anticipated | Delay while artifacts are protected, may require change of alignment or project limits to avoid the site resulting in delay and additional costs.
| Environmental | Endangered Species | Construction | Endangered species are discovered during construction, species present are added to endangered list | Delay while mitigations are developed and carried out, increased costs.
| ROW and Utilities | ROW Acquisition | Construction | Unable to acquire ROW, unable to gain access to site for the works | Delay while eminent domain is enacted, increase in cost due to escalation during delay
| ROW and Utilities | ROW Challenge | Construction | ROW acquisition process raises objections from land owners that lead to challenge to Environmental Approval, requires a Supplemental assessment and approval | Delay while Supplement is developed, increased costs and knock-on affect on construction schedule.
| ROW and Utilities | Utilities Budget | Construction | Utility relocation costs by Utility Companies exceed budgeted amounts | Cost overrun
| ROW and Utilities | Utility Works | Construction | Utility relocations are more extensive or complex than originally thought | Delay while additional works are carried out, cost overrun if utility budget has to be increased, potential claim by Contractor if access to site is restricted
| ROW and Utilities | Unforeseen Utilities | Construction | Utilities are discovered during the works that have to be relocated | Delay while relocations are design, Utility Companies contacted and works programmed and carried. Cost overrun due to works and potential claim by Contractor if access to site is restricted or works are stopped.
| ROW and Utilities | Utility Interruption | Construction | Utility interruption occurs during construction, e.g. water pipe bursts, gas main breaks etc | Delay while utilities are repaired by Utility Company, investigation may be required, workers or nearby residents may be hurt, Contractor may have to stop work. Increased costs due to repairs and disruption to works.
| Technical - Design | Design Standards | Construction | Discriminatory change in design standards | Delay while design is reviewed for impact of change and changes are made. Cost of re-design.
| Technical - Design | Project Requirements | Construction | Change in project specification or requirements such as restriction on truck use, or allowing truck use when it was initially restricted | Delay while design is reviewed for impact of change and changes are made. Cost of re-design.
| Technical - Design | Ground Conditions | Construction | Ground conditions assumed in design are different on site | Remedial works on structures and foundations resulting in delay and additional costs.
| Technical - Design | Hazardous Materials | Construction | Contaminated ground is uncovered on site | Delay while contaminated ground is removed and stored or disposed of in accordance with regulations and legal requirements.
| Technical - Design | Grading / Site Clearance | Construction | Additional work required | Cost overrun, delay
| Technical - Design | Earthworks | Construction | Additional work required | Cost overrun, delay
| Technical - Design | Roadway | Construction | Additional work required | Cost overrun, delay
| Technical - Design | Structures | Construction | Additional work required | Cost overrun, delay
| Technical - Design | Tunnels [IF APPLICABLE] | Construction | Additional work required | Cost overrun, delay
| Technical - Design | Roadside Equipment | Construction | Additional work required | Cost overrun, delay
| Technical - Design | Security | Construction | Increase in security requirements on site | Additional cost of security professionals and surveillance equipment. Delay if new procedures are introduced, e.g. ID checks.
| Technical - Design | Railroad Interface [IF APPLICABLE] | Construction | Interfaces with railroads can be complex and require unusual working conditions, additional permits etc that may not be envisaged during the design phase | Delay and disruption to accommodate requirements, additional cost.
| Technical - Design | Drainage | Construction | Insufficient drainage during construction, flooding | Potential for claims from residences and businesses adjacent to site, delay to works until flooding subsides or can be pumped out. Additional costs of disruption.
| Technical - Design | Existing Infrastucture [IF APPLICABLE] | Construction | Condition of existing infrastructure is worse than envisaged in the design in areas where the new roadway connects with existing facilities. | Re-design and additional construction results in delay and increased cost
| Technical - Design | Materials Quality | Construction | Poor quality of materials | Re-work required, delay and cost.
| Technical - Design | Materials Supply | Construction | Failure of materials supplier | Delay while new supply is located, may increase cost of materials.
| Technical - Design | Constructability | Construction | Unforeseen constructability issues | Conflict between aspects of design resulting in need for re-design and consequently increase in cost and delays.
| Technical - Design | Scope Change | Construction | Change of project requirements initiated by Agency | Change order will include cost and schedule impact. Reduction in scope should result in savings.
| Technical - Design | Performance - Main Contractor | Construction | Failure to construct according to design specification and required quality of works. | Work not completed on time, remedial works required. Costs increase and potentially termination of contract resulting in increased costs and delay while new contractor is procured.
| Technical - Design | Performance - Supply Chain | Construction | Failure of supply chain partners to deliver services or products, e.g. due to limited availability and expertise. | Disruption and delays to construction schedule necessitate additional costs/resources to maintain or accelerate scheduled progress
| Technical - Design | Labor Dispute | Construction | Dispute occurs between Unions and Agency over working conditions, pay etc. | Negotiations with unions result in delay to project.
| Technical - Design | Performance Dispute | Construction | Issues of dispute occur between the Agency & Contractor over performance of contractor or subcontractors during the construction of new works. | Claim later on.
| Technical - Design | Contract Coordination | Construction | If different contracts are used (structures, ITS etc) discrepancies between contracts can create difficulties in completion. | Difficulties in completion of overlapping contracts can require rework, with resulting cost and schedule increases
| Technical - Design | Design and Construction Admin and Oversight | Construction | Poor oversight during design, poor oversight during construction, unforeseen level of oversight required | Poor design oversight can result in delays to approvals and costly re-design. Poor construction oversight (QA/QC) can result in unsafe conditions during construction and also during operation. Remedial measures can cause delay and serious incidents later
| Technical - Design | Traffic Management | Construction | Unacceptable impact on public safety, road damage, congestion during construction | Revised procedures for traffic management, possibly increased cost if alternative routes to site have to be found or restrictions are placed on access and working times.
| Technical - Design | Testing & Commissioning | Construction | Constructed facilities are not approved for opening, including tolling system, lighting, ITS equipment | Cost to repair. Defect correction exceeds scheduled timeframe and float is insufficient resulting in delay to opening. Open without tolling, resulting in loss of revenue.
| Technical - Design | Latent Defects | Operations and Maintenance | Defects are discovered post completion of new works | Additional costs to remediate and rehabilitate defects
| Technical - Operations | Toll Violations [IF APPLICABLE] | Operations and Maintenance | Excessive toll violations due to failure of recognition equipment, transponders, enforcement, power cut. | Loss of toll revenue.
| Technical - Operations | Tolling Operation Center [IF APPLICABLE] | Operations and Maintenance | Operations center fails to function, such as due to a power outage, loss of communication systems (internet, phone), computer failure. | Delay and loss of toll revenue while systems are put back on line.
| Technical - Operations | Tolling Operations [IF APPLICABLE] | Operations and Maintenance | Organizational and management inefficiency from provider of back-end Electronic Tolling Collection activities (Customer Service Center and Video Enforcement Processing Center). | Increased tolling transaction costs
| Technical - Operations | Toll System Defects [IF APPLICABLE] | Operations and Maintenance | Defects occur in toll equipment | Loss of toll revenue.
| Technical - Operations | New Technology / Interoperability | Operations and Maintenance | Statewide or regional adoption of a new electronic tolling solution. Interoperability requirements are introduced and/or change. | Costs to adapt and introduce any required technology would be incurred.
| Technical - Operations | Incidents | Operations and Maintenance | Major accident involving third party collision with Asset or vehicle to vehicle collision | Road is deemed unsafe for use leading to closure until safety concerns are addressed - loss of toll revenue. Traffic congestion and diversion. Public perception of safety suffers.
| Technical - Operations | Operations Staffing | Operations and Maintenance | Limited availability of skilled resources or capability and experience is poor | Operation of asset does not benefit from efficient and effective management resulting in unplanned and creeping cost escalation
| Technical - Operations | Security | Operations and Maintenance | Increased security requirements | Additional cost of equipment and personnel.
| Technical - Operations | Handback Requirements | Operations and Maintenance | Facility is in poor condition at the end of the concession | Additional cost to bring the facility up to an acceptable condition
| Technical - Operations | Major Maintenance | Operations and Maintenance | Failure to carry out major maintenance | Deferred major maintenance results in more extensive and costly repairs or replacement which may exceed maintenance budget (extensive full depth pavement replacement, bridge deck replacement, etc)
| Technical - Operations | Routine Maintenance | Operations and Maintenance | Failure to carry out routine/ planned maintenance can lead to more serious defects. | Can lead to more serious defects and increased costs later on. May also result in a safety concern such as increased drainage, obstructions, debris etc.
| Technical - Operations | Management of Traffic | Operations and Maintenance | Renewal, upgrade and rehab works restrict the flow of traffic | If works are not carried out at times when traffic is low such as at night then congestion may result in loss of toll revenue. Carrying out works at night has safety impact on maintenance workers and may also increase costs if labor laws require additiona
| Technical - Operations | Drainage and Ponding | Operations and Maintenance | Ponding on roadway due to misplaced or blocked drains. | If ponding is not removed it can cause accidents, injuries, potential loss of life and damage to property and the asset. Impact is loss of toll revenue while crashes are cleared up and cost associated with any proven liability against incident management
| Technical - Operations | Flooding | Operations and Maintenance | Inadequate drainage. | Future weather patterns may result in more intense floods, damaging the assets or lessening usability through closures.
| Technical - Operations | Maintenance Standards | Operations and Maintenance | Change in operations and/ or maintenance standards. | Increased standards will increase cost and may cause loss of revenue if lane closure is required for unscheduled maintenance.
| Technical - Operations | Latent Defects | Operations and Maintenance | Existence of Construction Defects post completion of new works | Increased costs to operate and maintain the asset.
| Technical - Operations | Utilities | Operations and Maintenance | Maintenance of utilities and structures passing over or adjacent to roadway (e.g. power lines), restricted access for utility companies to investigate and repair. | Failure of third-party obligation to maintain utilities or structures affects usability of the asset. Safety concerns arise as damage may occur to customers' vehicles and occupants. Reliance on Authority and Federal Laws identifying third party public aut
| Technical - Operations | Maintenance Staffing | Operations and Maintenance | Limited availability of skilled resources or capability and experience is poor | Maintenance of asset does not benefit from efficient and effective management resulting in unplanned and creeping cost escalation
| Force Majeure | Major Storm, Earthquake, Terrorist Attack, War, Pandemic | Construction | Act of destruction during construction | Potential death or injury to workers; remedial work to repair damage resulting in cost and time delays.
| Force Majeure | Major Storm, Earthquake, Terrorist Attack, War, Pandemic | Operations and Maintenance | Act of destruction or threat to operation of facility | Potential death or injury to road users; remedial work to repair damage resulting in cost and time delays; loss of revenue if tolled.

## Risk Register Guide
Risk Register Guide
The Risk Register template can be obtained on the VAP3 website and used as a basis to create a project specific register. This template has example risks, which can easily be deleted. The Risk Register is a Microsoft Excel spreadsheet containing two separate spreadsheet tabs: 1. development and procurement risks, which occur prior to contract execution; and 2. implementation and operations risks, which occur after contract execution.
Risk Register Format
A title block is provided for the user to enter the project title and the name of the VAP3 project manager. Headings and footers describe the phase, page number and date of printing. The title block and header also allows the user to define the stage of assessment. The Risk Register is divided into “risk categories” for the major types of risk found in P3 projects. See the following tabs for examples.
Risk Register Content
The following is a description of the content in the Risk Register for both tabs described above. The tabs vary slightly and these differences are discussed below in more detail.
Risk Information
Each risk has its own risk number (column 1). The risks provided in the template are described by risk category (column 2), risk topic (column 3) and impact phase (column 4). The impact phase is any one of the five risk phases, excluding the screening phase, and relates to the timing of the impact of the risk event should it occur. If a risk has potential impact in more than one phase, a new line has to be added with identical category and topic, but with a different impact phase selected. Each risk has a risk description (column 5), which is an elaboration of the category/topic to describe the risk event. It should contain sufficient detail to be understood by any reader.
Risk Analysis
Each risk has a consequence (column 6), which should be a brief description of the potential consequence if the event should occur and provide a logical link between the event and its impacts. The consequence typically impacts cost or schedule but can be as specific as a safety, environmental, or reputation impact. The Red-Amber-Green (RAG) risk analysis involves the selection of a probability range in column 7 and cost and schedule consequence ranges from columns 8a and 8b respectively. At this stage of analysis, the assessment is limited to percentage ranges provided in drop-down menus in the Risk Register. The cost impact is a percentage of total project costs. Implementation phase schedule impacts are defined as a range of months delaying completion. Development phase cost impacts are defined as a percentage of project funds to reach financial close and schedule impacts are defined as a range of months delaying financial close. The spreadsheet contains a formula that calculates cost and schedule risk impact. The Risk Register contains a macro to automatically color the risk impact column based on the RAG Analysis described in the guidance. Colors may assist in the communication of risk results.
An Expected Value Analysis requires the estimation of a range of dollar values for cost and schedule impact. The range is defined by three values: a minimum (Min), most likely (ML) and maximum (Max). Columns 9, 10a and 10b allow the quantification of probability, cost consequence and schedule consequence in a similar manner to that described above but without the restriction of drop down menus. The Risk Register contains a simplified formula that combines the input values for probability and impact to calculate the risk value for use in this Risk Analysis. This formula is discussed in the guidance. As with the qualitative risk analysis, a total value for cost and schedule impact can be obtained by summing the “risk value” columns. Also, filters can be applied to the Risk Register to calculate separate amounts for the different Risk Response methods, including retained and transferred risks. Schedule impact may not be applicable for risks during the operations phase. Instead, an additional column 9.1 is provided as a free text box to describe the frequency of the risk impact. Typical frequency options include: every year, once over the whole analysis period, every 10 years, in the first 3 years of the analysis period, and in the last three years of the analysis period. This determination has been found to be useful during Risk Workshops to help attendees quantify risk impacts without getting confused about whether the event is annual or occurs at longer intervals through the operations period. Further analysis can be performed to annualize the risk values, or adjust different parts of the operations phase cost/revenue estimate. A Monte Carlo Simulation uses the same quantitative input data as the Expected Value Analysis, but instead of using a simple formula to approximate a weighted distribution of impact values, specialist software is used to perform a Monte Carlo Simulation (see Appendix E for discussion on the Monte Carlo Simulation), resulting in a range of probabilities and impacts. Consequentially, columns 9, 10a and 10b can be ignored. Instead column 10c is used if a Monte Carlo Simulation is performed as the definition of assumption curve replaces the simplified formula used in the Expected Value Analysis. Column 10c defines the assumption curve for each individual risk and any important modeling notes.
Risk Response, Assignment and Allocation
Having identified and assessed the risks, the VAP3 Project Manager and project team determine what the Agency’s initial response is likely to be. Column 11 allows the user to define an overall Risk Response strategy from a drop-down menu of five options (1) avoidance; (2) transference; (3) acceptance; (4) mitigation; and (5) sharing. These options are described in Section 3.1.2 – Step 3. Column 12 allows the user to select a party that is to be allocated the risk. The menu of options includes: (1) the Agency (for retained risks); (2) the contractor (for transferred risks under a design-bid-build or design-build approach); (3) the concessionaire (for transferred risks under a design-build-finance-operate-maintain approach); and (4) shared. A table of typical allocations for different methods of procurement for transportation highway projects is provided in the guidance. Risk Allocation notes to explain key assumptions and rationale for the allocation should be added to column 13. As the project progresses, more information is likely to be available for a determination of Risk Response and allocation. These columns should be updated and notes added.
Risk Tracking
The column 14 provides the user with an opportunity to track risks via a record of risk owner, a more detailed description of response/mitigation strategy, estimated mitigation cost (if known), risk review date, status/comments and whether the risk is on the critical path or not. Critical path risks may require a more detailed analysis of schedule risk impacts.
Notes
If risks are closed during later stages of analysis this can be shown in column 15 and the entire risk row can be “grayed out”. This approach is better than deleting the risk row entirely so that you have a record of having considered the issue, which is important for capturing and feeding back lessons learned. The reason for closure should be added to column 15. Notes may be added to column 16 to state any lessons learned regarding a specific risk or the Risk Management Framework and/or the relevant section in the contract documents, which discusses the Risk Allocation.

## Instructions
INSTRUCTIONS ON HOW TO COPY THIS TEMPLATE
PLEASE NAVIGATE TO FILE THEN CLICK ON MAKE A COPY (SEE ATTACHED IMAGE BELOW)