## Risk Tracking Template
Risk Tracking Template
Date of last review:
ID | Description of Risk | Impact | Risk Reponse | Risk Level | Risk owner | Notes
1 | Supplier delay | Pushes launch | Confirm delivery dates by Phase 2 | High | Clarissa | SAMPLE
2 | Factory availability | Cost overruns | Stakeholder trip to China | High | Dave, Rajesh & Nina | SAMPLE
3 | Steering committee unavailable | Delay launch marketing | Define marketing plans in March | Low | Tyrell | SAMPLE
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
Related Free Templates
Dashaboard Template
Issue Tracking Template
Change Log Template

## How to Use this Template
Introduction
A risk tracking template allows you to identify and track any risks that might appear in your project. It's critical to track risks in your projects, so they don't become issues that derail progress. A risk tracking template is a living document, and should be frequently inspected and updated.
Definition of Terms
ID: The identification number of your risk.
Description of Risk: Provide a brief description of your risk that anyone can understand.
Impact: Outline the potential impact that risk can have on your project.
Risk Response: Describe what your reaction to the risk is, in order to quell it.
Risk Level: Define the priority of the risk; how likely it is to affect your project.
Risk Owner: Define the team member or manager in charge of monitoring the risk.
Notes: Add any notes you may have for a better understanding of the risk. Update regularly.