## Risk Register Translation and A
ID | Asset | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Level | Acceptance Level | Treatment Strategy | (ISO 27001 Annex A) | Polices
R-01 | Employee Data | External Breach | Lack of Multi-Factor Authentication (MFA) | 4 | 5 | 20 | Rejected | Treat | A.5.15 Access control | Information Security Policy Password Policy
R-02 | Laptops | Theft / Loss | Lack of Disk Encryption | 2 | 4 | 8 | Temporarily Accepted | Treat | A.8.1 User endpoint devices
R-03 | Data Center | Power Outage | Lack of Backup Generators | 1 | 5 | 5 | Accepted | Accept | A.7.10 Storage media
R-04 | Emails | Social Engineering | Lack of Employee Awareness | 5 | 4 | 20 | Rejected | Treat | A.6.3 Information security awareness
R-05 | Amazon S3 | Data Breach | WAF MisConfiguration – Over privleged IAM | 4 | 5 | 20 | Rejected | Treat
R-06 | Harddisks | Data Breach | Lack of Encryption | 2 | 4 | 8 | Rejected | Treat | Encryption
R-07 | E-mail Server | Dos/Ddos, spam and phishing | Dos/Ddos, Social Engineering | 5 | 5 | 25 | Rejected | Treat | Use of cryptography, User end point devices, Secure authentication, Logging, Monitoring activities, | Email Policy, cryptography Policy,
R-08 | [5 empty] | 0
R-09 | [5 empty] | 0
R-10 | [5 empty] | 0