## Guidance
Implementation Guidance
(this section must be removed from final version of the document)
Purpose of this document
This document should be used to plan the project to implement improvements and changes to meet the requirements of the GDPR.
Areas of the standard addressed
All areas of the GDPR are covered.
General Guidance
This is an Excel version of a project plan that is also supplied in Microsoft Project format within the toolkit. It is intended for those users that do not have access to Microsoft Project. If you do have Project then we suggest you use that instead of this spreadsheet as it provides better project management functionality. The plan includes the main tasks involved in such a project, from initiation through to initial compliance. You will need to decide on the likely duration of each of the tasks and update the resources that we have allocated to suit your own organisation. It is difficult to reflect task dependencies within a spreadsheet but putting the tasks in approximate order of implementation will help to track progress.
Review Frequency
The plan should be used on a regular basis to track progress and understand the impact of any delays on the final end date of the project.
Toolkit Version Number
GDPR Toolkit Version 5
Copyright notice
Except for any third party works included in this document, as identified in this document, this document has been authored by CertiKit, and is © copyright CertiKit except as stated below. CertiKit is a company registered in England and Wales with company number 6432088.
Licence terms
This document is licensed on and subject to the standard licence terms of CertiKit, available on request, or by download from our website. All other rights are reserved. Unless you have purchased this product you only have an evaluation licence. If this product was purchased, a full licence is granted to the person identified as the licensee in the relevant purchase order. The standard licence terms include special terms relating to any third party copyright included in this document.
Disclaimer
Please Note: Your use of and reliance on this document template is at your sole risk. Document templates are intended to be used as a starting point only from which you will create your own document and to which you will apply all reasonable quality checks before use. Therefore please note that it is your responsibility to ensure that the content of any document you create that is based on our templates is correct and appropriate for your needs and complies with relevant laws in your country. You should take all reasonable and proper legal and other professional advice before using this document. CertiKit makes no claims, promises, or guarantees about the accuracy, completeness, or adequacy of our document templates, assumes no duty of care to any person with respect its document templates or their contents, and expressly excludes and disclaims liability for any cost, expense, loss or damage suffered or incurred in reliance on our document templates, or in expectation of our document templates meeting your needs, including (without limitation) as a result of misstatements, errors and omissions in their contents.

## Project Plan
[Note: to choose a different table layout, click in the table, select the Design menu ribbon and choose a table style]
GDPR Preparation Project Plan
NOTE: All tasks and resources assigned are approximations and will depend on the specifics of your project. If appointed, the Data Protection Officer may take the role of Project Lead.
Ref. | Task | Main GDPR Reference | Effort (man-days) | Resource | Progress | Status | Start Date | End Date
1 | GDPR preparation project
1.1 | Perform gap assessment |  |  | Project Manager, Project Lead | 0% | Not started
1.2 | Gain senior management commitment |  |  | Project Manager, Project Lead | 0% | Not started
1.3 | Initiate project with appropriate resources and budget |  |  | Project Manager | 0% | Not started
1.4 | Establish document control |  |  | Project Manager | 0% | Not started
2 | GDPR roles, awareness and training
2.1 | Conduct communication programme to suppliers and other stakeholders |  |  | Project Lead | 0% | Not started
2.2 | Define GDPR roles and responsibilities |  |  | Project Lead, Senior Management | 0% | Not started
2.3 | Identify lead Data Protection Supervisory Authority |  |  | Project Lead, Senior Management, Legal | 0% | Not started
2.4 | Appoint Data Protection Officer (if required) | CHAPTER IV - Section 4 - Data protection officer |  | Senior Management | 0% | Not started
2.6 | Conduct GDPR competence and training needs assessment | CHAPTER IV - Section 4 - Data protection officer |  | Project Lead | 0% | Not started
2.7 | Perform GDPR-related training and familiarisation | CHAPTER IV - Section 4 - Data protection officer |  | Project Lead | 0% | Not started
2.8 | Conduct GDPR and information security awareness training | CHAPTER IV - Section 4 - Data protection officer |  | Project Lead, Information Security Manager | 0% | Not started
3 | Personal data mapping
3.1 | Conduct initial personal data information gathering exercise | CHAPTER II - Principles |  | Project Lead | 0% | Not started
3.2 | Perform audit of personal data by business area | CHAPTER II - Principles |  | Business Area Leads | 0% | Not started
3.3 | Identify lawful basis for processing personal data in each case | Article 6 - Lawfulness of processing |  | Business Area Leads, Legal | 0% | Not started
3.4 | Conduct legitimate interest assessments where required | Article 6 - Lawfulness of processing |  | Business Area Leads, Legal | 0% | Not started
3.5 | Identify record-keeping requirements and procedures | Article 30 - Records of processing activities |  | Project Lead | 0% | Not started
4 | Privacy policies and notices
4.1 | Define personal data retention and protection policy | Article 5 - Principles relating to processing of personal data |  | Project Lead, Business Area Leads, Legal | 0% | Not started
4.2 | Create or amend existing privacy notices | Articles 13 and 14 - Information to be provided |  | Business Area Leads | 0% | Not started
4.3 | Review and amend consent methods and procedures | Article 7 - Conditions for consent |  | Business Area Leads | 0% | Not started
4.4 | Address age-related consent and controls (children) | Article 8 - Conditions applicable to child's consent |  | Business Area Leads | 0% | Not started
5 | Rights of the data subject
5.1 | Create and implement data subject request procedures | CHAPTER III - Rights of the data subject |  | Project Lead | 0% | Not started
5.2 | Start recording data subject requests | CHAPTER III - Rights of the data subject |  | Data Subject Request Administrator | 0% | Not started
6 | Controllers and processors
6.1 | Update contracts with processors to be GDPR compliant | CHAPTER IV - Section 1 - General obligations |  | Legal | 0% | Not started
6.2 | Distribute supplier questionnaires regarding personal data protection | CHAPTER IV - Section 1 - General obligations |  | Legal | 0% | Not started
6.3 | Provide information to controllers for whom we act as a processor | CHAPTER IV - Section 1 - General obligations |  | Legal, IT Management | 0% | Not started
6.4 | Update contracts with controllers to be GDPR compliant | CHAPTER IV - Section 1 - General obligations |  | Legal | 0% | Not started
6.5 | Address employee confidentiality requirements | CHAPTER IV - Section 1 - General obligations |  | Human Resources | 0% | Not started
7 | Data protection impact assessment
7.1 | Define data protection impact assessment process | CHAPTER IV - Section 3 - Data protection impact assessment |  | Project Lead | 0% | Not started
7.2 | Conduct data protection impact assessment training | CHAPTER IV - Section 3 - Data protection impact assessment |  | Project Lead | 0% | Not started
7.3 | Perform initial data protection impact assessment | CHAPTER IV - Section 3 - Data protection impact assessment |  | Business Area Leads | 0% | Not started
8 | International transfers
8.1 | Identify international transfers of personal data | CHAPTER V - Transfers of personal data to third countries |  | Project Lead, Business Area Leads, Legal | 0% | Not started
8.2 | Assess legality of existing international transfers | CHAPTER V - Transfers of personal data to third countries |  | Legal | 0% | Not started
8.3 | Put in place agreements for international transfers of personal data (where required) | CHAPTER V - Transfers of personal data to third countries |  | Legal | 0% | Not started
9 | Personal data breach management
9.1 | Create information security incident management procedure | CHAPTER IV - Section 2 - Security of personal data |  | Project Lead, Information Security Manager | 0% | Not started
9.2 | Create personal data breach notification procedure | CHAPTER IV - Section 2 - Security of personal data |  | Project Lead | 0% | Not started
9.3 | Conduct information security incident management training | CHAPTER IV - Section 2 - Security of personal data |  | Project Lead, Information Security Manager | 0% | Not started
9.4 | Test incident management and breach notification procedures | CHAPTER IV - Section 2 - Security of personal data |  | Project Lead, Information Security Manager | 0% | Not started
10 | Project closure
10.1 | Repeat gap assessment to identify remaining non-compliant areas |  |  | Project Manager, Project Lead | 0% | Not started
10.2 | Address any remaining non-compliant areas |  |  | Project Manager, Project Lead | 0% | Not started
10.3 | Perform post-project review |  |  | Project Manager, Project Lead, Business Area Leads, Legal, IT Management, Senior Management | 0% | Not started