Business Continuity Management System Project Initiation Document

ISO22301 Toolkit: Version 6
©CertiKit

Implementation guidance

The header page and this section, up to and including Disclaimer, must be removed from the final version of the document. For more details on replacing the logo, yellow highlighted text and certain generic terms, see the Completion Instructions document.

Purpose of this document

This document defines what the project is to achieve, and the resources allocated to its success.

Areas of the standard addressed

The following areas of the ISO22301 standard are addressed by this document:

4. Context of the organization

  - 4.3 Determining the scope of the business continuity management system

5. Leadership

  - 5.1 Leadership and commitment

6. Planning

General guidance

A well written and agreed Project Initiation Document (PID) is essential to defining what the project is intended to achieve and clarifying what is in and out of scope. The PID may be one of the most important documents in your BCMS as it sets out the resources and timescales that will be used to establish the BCMS in the first instance.

Use the PID to gain consensus and commitment from management and staff to the implementation of the management system and the achievement of certification to the ISO22301 standard.

Review frequency

The PID should be reviewed regularly throughout the project to ensure that the objectives set remain relevant and the expected business benefits will still be obtained.

Document fields

This document may contain fields which need to be updated with your own information, including a field for Organization Name that is linked to the custom document property “Organization Name”.

To update this field (and any others that may exist in this document):

- Update the custom document property “Organization Name” by clicking File > Info > Properties > Advanced Properties > Custom > Organization Name.

- Press Ctrl A on the keyboard to select all text in the document (or use Select, Select All via the Editing header on the Home tab).

- Press F9 on the keyboard to update all fields.

- When prompted, choose the option to just update TOC page numbers.

If you wish to permanently convert the fields in this document to text, for instance, so that they are no longer updateable, you will need to click into each occurrence of the field and press Ctrl Shift F9.

If you would like to make all fields in the document visible, go to File > Options > Advanced > Show document content > Field shading and set this to “Always”. This can be useful to check you have updated all fields correctly.

Further detail on the above procedure can be found in the toolkit Completion Instructions. This document also contains guidance on working with the toolkit documents with an Apple Mac, and in Google Docs/Sheets.

Copyright notice

Except for any specifically identified third-party works included, this document has been authored by CertiKit, and is ©CertiKit except as stated below. CertiKit is a company registered in England and Wales with company number 6432088.

Licence terms

This document is licensed on and subject to the standard licence terms of CertiKit, available on request, or by download from our website. All other rights are reserved.  Unless you have purchased this product you only have an evaluation licence.

If this product was purchased, a full licence is granted to the person identified as the licensee in the relevant purchase order. The standard licence terms include special terms relating to any third-party copyright included in this document.

Disclaimer

Please Note: Your use of and reliance on this document template is at your sole risk. Document templates are intended to be used as a starting point only from which you will create your own document and to which you will apply all reasonable quality checks before use.

Therefore, please note that it is your responsibility to ensure that the content of any document you create that is based on our templates is correct and appropriate for your needs and complies with relevant laws in your country.

You should take all reasonable and proper legal and other professional advice before using this document.

CertiKit makes no claims, promises, or guarantees about the accuracy, completeness or adequacy of our document templates; assumes no duty of care to any person with respect its document templates or their contents; and expressly excludes and disclaims liability for any cost, expense, loss or damage suffered or incurred in reliance on our document templates, or in expectation of our document templates meeting your needs, including (without limitation) as a result of misstatements, errors and omissions in their contents.

Business Continuity Management System Project Initiation Document

| DOCUMENT REF | BCMS-DOC-00-1 |
| --- | --- |
| VERSION | 1 |
| DATED | [Insert date] |
| DOCUMENT AUTHOR | [Insert name] |
| DOCUMENT OWNER | [Insert name/role] |

Revision history

| VERSION | DATE | REVISION AUTHOR | SUMMARY OF CHANGES |
| --- | --- | --- | --- |

Distribution

| NAME | TITLE |
| --- | --- |

Approval

| NAME | POSITION | SIGNATURE | DATE |
| --- | --- | --- | --- |

Contents

1	Introduction	9

2	Objectives and benefits	10

3	Scope, dependencies, constraints and assumptions	11

3.1	In scope	11

3.2	Out of scope	11

3.3	Project dependencies	11

3.4	Constraints	11

3.5	Assumptions	12

4	Project organization and authorities	13

4.1	Project organization	13

4.1.1	Project board	13

4.1.1.1	Project sponsor	13

4.1.1.2	Project manager	13

4.1.1.3	Senior supplier	14

4.1.1.4	Senior user	14

4.1.2	Project team	14

5	Project resources	15

5.1	Human resources	15

5.2	Technical resources	15

5.3	Information resources	15

5.4	Financial resources	16

6	Timescales and milestones	17

7	Project communication	18

7.1	Interested parties	18

7.2	Project progress reporting	18

7.3	RAID log	18

8	Deliverables	19

9	Initial project risk assessment	20

10	Initial Project Plan	21

Tables

Table 1: Project dependencies	11

Table 2: Project board members	13

Table 3: Project team members	14

Table 4: Human resources	15

Table 5: Technical resources	15

Table 6: Information resources	15

Table 7: Financial resources	16

Table 8: Project milestones	17

Table 9: Interested parties	18

Table 10: Project deliverables	19

Table 11:Initial risk assessment	20

# Introduction

The ability of our business to keep going in the face of an unexpected event that disrupts its operation is a key factor in demonstrating to our customers, suppliers and other interested parties that we are a professional, reliable organization that is worth dealing with. Much work has already been done to make our business activities more resilient in the face of an uncertain and continually changing world. The objective of this project is to obtain third party recognition of our readiness for business continuity in order to prove to ourselves, and those that matter, that we have successfully adopted best practice and have the right systems in place to recover from a disruptive incident.

The International Standard for business continuity, ISO22301, was published by the ISO in 2012 and was updated in 2019. This was a development of the earlier British Standard, BS25999 and describes the actions necessary to establish an effective Business Continuity Management System (BCMS).

In [Date] a gap analysis was undertaken to assess the current level of conformity against the ISO22301 standard. This concluded that the organization is currently X% conformant to the standard’s requirements and that, although many of the necessary business continuity activities are carried out, they are done so informally and are therefore not evidenced as fully as needed. Based on the conclusions of this report, [Organization Name] has decided to pursue full certification to ISO22301 in order that the effective adoption of business continuity best practice may be validated by a Registered Certification Body (RCB).

This document is intended to act as a formal starting point for the project to undertake the work that needs to be done within [Organization Name] to enhance its business continuity processes and procedures and bring them in line with the standard.

# Objectives and benefits

The objectives of this BCMS project are as follows:

- To achieve certification to the international standard for business continuity, ISO22301, within a XX-month timeframe

- To establish a more proactive business continuity framework within [Organization Name] in line with business requirements

- To implement best practice in business continuity so that the organization’s business processes are better protected

- To increase the awareness of [Organization Name] staff of business continuity issues

Achievement of ISO22301 certification will require [Organization Name] to invest time and money into the initial implementation project and the ongoing maintenance of the processes involved. It is important to be clear from the outset about the benefits that such a route is expected to deliver. As with many quality initiatives, it is difficult to put a monetary figure on the difference that certification will make (although sometimes this is possible if factors such as the cost of past disruptive incidents can be estimated).

However, from experience of previous implementations in other organizations of similar size it would be reasonable to anticipate the following major areas of benefit:

Significantly reduced risk of harm, loss, or embarrassment due to business continuity incidents

Provides peace of mind to our customers, staff, board members, suppliers and other interested parties that business continuity has been addressed

Demonstrates that [Organization Name] takes business continuity seriously

Internal and external recognition of the quality of the business continuity processes and plans in place

Year-on-year improvement in the continuity of the organization’s business processes as a result of the continuous improvement aspects of the standard

A strong move away from reactive firefighting towards proactive reduction of disruptive incidents

Better alignment of business continuity policies and plans with the needs of the business through regular review meetings with interested parties

Better perception and awareness of business continuity issues within the business as a whole

Steps will be taken where possible to quantify the achievement of the project against these anticipated benefits.

# Scope, dependencies, constraints and assumptions

## In scope

[Define the areas within the scope of the project. This may be expressed in terms of geographical or organizational boundaries, systems, processes or any other factor that helps to define what is included.]

For the purposes of ISO22301 certification, the boundaries of the certification are defined as follows:

“All locations, business processes, products and services within [Organization Name]”

## Out of scope

[Define the areas that are outside the scope of the project. This may be expressed in terms of geographical or organizational boundaries, systems, processes or any other factor that helps to define what is excluded.]

## Project dependencies

This project has the following inter-dependencies with other projects either planned or in progress within the organization:

| PROJECT | NATURE OF DEPENDENCY | TIMESCALE |
| --- | --- | --- |

Table 1: Project dependencies

## Constraints

The following constraints are applied to this project:

The project must be achieved within the stated timescale

Although limited financial resources are available, no specific budget has been allocated to this project, over and above the cost of the business continuity consultant

The business continuity consultant is assigned to the project x days per week

The project will be taking place at the same time as several other projects and so will need to compete for resources on a priority basis, decided by the [Finance Director]

## Assumptions

In preparing this Project Initiation Document, it is assumed that:

Business Managers are willing and available to participate in regular BCMS review meetings

Enough financial resources are available when required for any necessary expenditure recommended by the project

Enough human resource is available to progress the project in a timely fashion

[State any additional assumptions]

# Project organization and authorities

It is important to define the way in which the project will be organized so that clear management direction will be possible.

## Project organization

The project will be overseen by a project board which will have primary responsibility for the governance of the project and the achievement of its objectives.

### Project board

The project board will consist of:

| ROLE | NAME | TITLE |
| --- | --- | --- |
| Project Sponsor | [Finance Director] |  |
| Project Manager | [Business Continuity Manager] |  |
| Senior Supplier | [Business Continuity Consultant] [Software tool Vendor] |  |
| Senior User | [Business Manager] |  |

Table 2: Project board members

The high-level project board roles, responsibilities and authorities are:

#### Project sponsor

Review and approval of project documentation

Review and approval of processes defined by the project

Approval of project change control

Ad-hoc direction

Approval of project closure

#### Project manager

Ensure the desired outcome of the project is specified and success criteria measured

Manage the production of the required products

Plan and monitor the project

Take responsibility for overall progress against plan

Management of risks and issues

Identification and management of project changes

Project reporting and communication

#### Senior supplier

Attend project board meetings

Represent the interests of the supplier resources under their control

#### Senior user

Attend project board meetings

Represent the interests of the intended business participants in the BCMS

### Project team

The achievement of the project deliverables will be undertaken by the project team. The project team will consist of the following people:

| ROLE | NAME | TITLE |
| --- | --- | --- |
| [Process owners] |  |  |
| [Technical staff] |  |  |

Table 3: Project team members

The responsibilities of a Project Team Member are as follows:

Input to one or more of the required products

Review of project documentation and products

Attendance at project meetings

# Project resources

The following resources will be allocated to the project by top management.

## Human resources

The following people will be available to the project for the periods specified:

| NAME | ROLE | PERIOD AVAILABLE | COMMITTMENT |
| --- | --- | --- | --- |
| [Name] | Project Manager | 6 months | 5 days per week |
| [Name] | Business lead | 3 months | 2 days per week |
| Etc. |  |  |  |

Table 4: Human resources

## Technical resources

The following technical resources will be allocated to the project:

| RESOURCES | PURPOSE | PROVIDED BY |
| --- | --- | --- |
| Server capacity | Test IT recovery plans | Service Delivery team |
| Network capacity | Connectivity for testing | Networks team |

Table 5: Technical resources

## Information resources

Information resources allocated to the project are as follows:

| RESOURCE | PURPOSE | PROVIDED BY |
| --- | --- | --- |
| Business process mappings | Assist with understanding of processing requirements and dependencies | Quality management |

Table 6: Information resources

## Financial resources

The following financial resources are available to the project.

| RESOURCES | AMOUNT | AVAILIBILITY |
| --- | --- | --- |
| Capital budget | USD 150,000 | FY 20xx – FY20yy |
| Revenue Budget | USD 80,000 p.a. | Ongoing |

Table 7: Financial resources

# Timescales and milestones

The planned timescale of the project is to deliver the BCMS by [expected live date].

Within the overall timescale of the project, it is envisaged that the following milestones will be achieved:

| MILESTONE | TIMEFRAME |
| --- | --- |
| Project Initiation | [specify date] |
| Gap Analysis | [specify date] |
| All required processes in place | [specify date] |
| Stage One Review | [specify date] |
| Stage Two Audit | [specify date] |

Table 8: Project milestones

Progress against these milestones will be tracked as part of project reporting and reviewed at project board meetings.

# Project communication

## Interested parties

Within the given scope of the project the following may be interested parties in the BCMS:

| PARTY | NATURE OF INTEREST | COMMUNICATION METHOD |
| --- | --- | --- |
| Project Board | Ensure project is successful | Weekly highlight reports |
| Organization staff | How change will affect current jobs | Monthly updates via existing magazine |
| Business Managers | When new plans and procedures will be in force | Mailshot programme in run-up to go-live |

Table 9: Interested parties

## Project progress reporting

The project manager will produce a [weekly] highlight report for the project board, detailing progress last week, work scheduled for next week, issues outstanding and an estimate of the latest degree of compliance against the ISO22301 standard.

## RAID log

The project manager will maintain a RAID log to record:

R: Risks to the success of the project

A: Actions agreed during project meetings

I: Issues that are affecting the project

D: Decisions made during the project

This log will be reviewed at each scheduled project meeting and upon significant changes affecting the project. The initial risks identified in this project initiation document will be used as a starting point.

# Deliverables

The following major deliverables will be created as part of this project:

| REF | DELIVERABLE | DESCRIPTION |
| --- | --- | --- |
| 1. | ISO22301 Gap Analysis | Assesses the current situation within [Organization Name] and what needs to be done to achieve the ISO22301 standard |
| 2. | Project Initiation Document | Defines the scope, resources, deliverables, timescales etc. of the project |
| 3. | Business Continuity Policy | Defining the overall approach to business continuity within the organization |
| 4. | Procedures and plans to implement the policy | A significant set of documentation to ensure the principles set out in the policy are followed |
| 5. | Business Impact Assessment Process | Sets out how business impact assessments will be carried out |
| 6. | Business Impact Assessments | Details of the effects of an inability to deliver key business activities over time |
| 7. | Risk Assessment Process | How risk assessment will be performed |
| 8. | Risk Assessment reports | Results of risk assessment using the chosen methodology |
| 9. | Risk Treatment Plan | What will be done about the identified risks |
| 10. | Procedures for planning, operation and control of processes | Process flows for the way the BCMS operates |
| 11. | Business continuity strategies and solutions | The approaches to be taken in different scenarios, and the individual solutions defined to support them |
| 12. | Business continuity plans and procedures | Methods of invoking and managing strategies and solutions, including the procedures to be used |
| 13. | Business continuity records | Minutes of meetings, reviews, tests |
| 14. | Training and awareness programs | Combination of formal training for key staff and briefings for ideally all other staff |
| 15. | Audit reports | From internal and external audits |
| 16. | Management reviews | Regular assessments by top management of the adequacy of the BCMS |
| 17. | [Add further deliverables] |  |

Table 10: Project deliverables

# Initial project risk assessment

At this initial stage, the following potential risks to the project have been identified:

| RISK | IMPACT | LIKELIHOOD | SCORE | TREATMENT |
| --- | --- | --- | --- | --- |
| Loss of Key Staff | High | Low | MEDIUM | Involve staff in the project; encourage development via appropriate training |
| Lack of Business Buy-in to project | High | Low | MEDIUM | Involve business management; ensure regular and clear communication of project goals, benefits and progress |
| Insufficient resources | High | Medium | HIGH | Monitor progress against plan; raise issues to Project Sponsor if appropriate; delay project if required |
| [Add further risks] |  |  |  |  |

Table 11:Initial risk assessment

The initial treatment actions identified above will be taken by the project manager in order to address these risks. These, and additional risks that are identified during the project, will be managed by the project manager.

# Initial Project Plan

[Insert a copy of the initial project plan]