## Project Plan
NOTE: All tasks and resources are approximations and will depend on the specifics of your project.
REF | TASK | MAIN ISO22301 REF | RESOURCE | START DATE | WORK DAYS | END DATE | COMPLETED DAYS | PROGRESS
1 | Project initiation | All | Project Mgr | 4398400% | 5 | 4399000% | 1 | 20%
2 | Define proposed scope of BCMS | 4.3 Determining the scope of the business continuity management system | Top Mgt,BC Manager | 4398500% | 3 | 4398700% | 1 | 33.33%
3 | Perform gap assessment | All | BC Manager,Business Reps | 4398600% | 1 | 4398600% | 1 | 100%
4 | Obtain Top Management commitment | 5.1 Leadership and commitment | BC Manager,Project Mgr,Top Mgt | 4398700% | 10 | 4400000% | 1 | 10%
5 | Establish BCMS document control | 7.5 Documented information | BC Manager,Project Mgr | 4398800% | 6 | 4399700% | 5 | 83.33%
6 | Define business continuity policy | 5.2 Policy | BC Manager,Top Mgt | 4398900% | 8 | 4399900% | 2 | 25%
7 | Document context of the organization | 4. Context of the organization | BC Manager,Top Mgt | 4399000% | 5 | 4399400% | 2 | 40%
8 | Agree business continuity objectives | 6.2 Business continuity objectives and planning to achieve them | BC Manager,Top Mgt | 4399100% | 10 | 4400400% | 2 | 20%
9 | Define roles, responsibilities and authorities | 5.3 Roles, responsibilities and authorities | BC Manager,Top Mgt | 4399200% | 6 | 4399900% | 2 | 33.33%
10 | Competence and training needs assessment | 7.2 Competence | BC Manager,Business Reps | 4399300% | 12 | 4400800% | 2 | 16.67%
11 | Conduct business impact analysis | 8.2 Business impact analysis and risk assessment | BC Manager,Business Reps,CIO | 4399400% | 1 | 4399400% | 1 | 100%
12 | Perform risk assessment | 8.2 Business impact analysis and risk assessment | BC Manager,Top Mgt,CIO | 4399500% | 2 | 4399800% | 2 | 100%
13 | Determine business continuity strategies and solutions | 8.3 Business continuity strategies and solutions | BC Manager,Top Mgt,CIO | 4399600% | 3 | 4399900% | 2 | 66.67%
14 | Establish business continuity plans | 8.4 Business continuity plans and procedures | BC Manager,Business Reps,CIO | 4399700% | 5 | 4400100% | 2 | 40%
15 | Plan business continuity exercising and testing | 8.5 Exercise programme | BC Manager,CIO,Top Mgt | 4399800% | 8 | 4400700% | 6 | 75%
16 | Document communications procedures | 8.4 Business continuity plans and procedures | BC Manager,Business Reps | 4399900% | 1 | 4399900% | 0 | 0%
17 | Define approach to monitoring, measurement, analysis and evaluation | 9.1 Monitoring, measurement, analysis and evaluation | BC Manager,Top Mgt | 4400000% | 1 | 4400000% | 1 | 100%
18 | Awareness training | 7.3 Awareness | BC Manager,Business Reps | 4400100% | 1 | 4400100% | 0 | 0%
19 | Establish continual improvement process | 10. Improvement | BC Manager,Top Mgt | 4400200% | 2 | 4400500% | 1 | 50%
20 | Internal audit | 9.2 Internal audit | BC Manager,Business Reps,CIO,Internal Audit Team | 4400300% | 6 | 4401100% | 3 | 50%
21 | Perform management review | 9.3 Management review | BC Manager,Top Mgt | 4400400% | 5 | 4400800% | 0 | 0%
22 | Certification stage one | All | BC Manager,Top Mgt,External Auditor | 4400500% | 8 | 4401400% | 0 | 0%
23 | Certification stage two | All | BC Manager,Business Reps,External Auditor,Top Mgt | 4400600% | 1 | 4400600% | 0 | 0%
24 | Post Project Review | All | Project Mgr,BC Manager,Top Mgt | 4400700% | 2 | 4400800% | 0 | 0%
Formulas:
END DATE = IFERROR(WORKDAY.INTL(ProjectPlanData[[#This Row],[START DATE]]-1,ProjectPlanData[[#This Row],[WORK DAYS]],1),"")
ISO22301 Project Plan
BCMS-DOC-00-4

## Project Budget
NOTE: Budget items will depend on the specifics of your project.
ITEM | BUDGET | SPENT TO DATE | BUDGET REMAINING
Internal resources | 5000 | 1500 | 3500
Training | 1500 | 500 | 1000
Travel and subsistence | 1500 | 600 | 900
External Consultancy | 2000 | 1000 | 1000
Communication | 1200 | 600 | 600
Professional memberships | 500 | 0 | 500
Software tools | 2500 | 1200 | 1300
Hardware | 3000 | 2000 | 1000
Offices and furniture | 1000 | 1000 | 0
Internal auditing | 500 | 250 | 250
Certification auditing | 500 | 0 | 500
Total | 19200 | 8650 | 10550

## Project Gantt Chart
Project Timeline
2-June-2020 to 2-July-2020 | [7 empty] | To refresh chart data, click on “Refresh All” on the Data ribbon.
Date display slider | [7 empty] | Not started |  |  |  | In progress |  |  |  | Completed |  |  |  | Weekends (Sat - Sun)
REF | TASK | RESOURCE | START DATE | WORK DAYS | END DATE | COMPLETED DAYS | PROGRESS | 2020-06-02 | 2020-06-03 | 2020-06-04 | 2020-06-05 | 2020-06-06 | 2020-06-07 | 2020-06-08 | 2020-06-09 | 2020-06-10 | 2020-06-11 | 2020-06-12 | 2020-06-13 | 2020-06-14 | 2020-06-15 | 2020-06-16 | 2020-06-17 | 2020-06-18 | 2020-06-19 | 2020-06-20 | 2020-06-21 | 2020-06-22 | 2020-06-23 | 2020-06-24 | 2020-06-25 | 2020-06-26 | 2020-06-27
1 | Project initiation | Project Mgr | 4398400% | 5 | 4399000% | 1 | 20%
2 | Define proposed scope of BCMS | Top Mgt,BC Manager | 4398500% | 3 | 4398700% | 1 | 33.33%
3 | Perform gap assessment | BC Manager,Business Reps | 4398600% | 1 | 4398600% | 1 | 100%
4 | Obtain Top Management commitment | BC Manager,Project Mgr,Top Mgt | 4398700% | 10 | 4400000% | 1 | 10%
5 | Establish BCMS document control | BC Manager,Project Mgr | 4398800% | 6 | 4399700% | 5 | 83.33%
6 | Define business continuity policy | BC Manager,Top Mgt | 4398900% | 8 | 4399900% | 2 | 25%
7 | Document context of the organization | BC Manager,Top Mgt | 4399000% | 5 | 4399400% | 2 | 40%
8 | Agree business continuity objectives | BC Manager,Top Mgt | 4399100% | 10 | 4400400% | 2 | 20%
9 | Define roles, responsibilities and authorities | BC Manager,Top Mgt | 4399200% | 6 | 4399900% | 2 | 33.33%
10 | Competence and training needs assessment | BC Manager,Business Reps | 4399300% | 12 | 4400800% | 2 | 16.67%
11 | Conduct business impact analysis | BC Manager,Business Reps,CIO | 4399400% | 1 | 4399400% | 1 | 100%
12 | Perform risk assessment | BC Manager,Top Mgt,CIO | 4399500% | 2 | 4399800% | 2 | 100%
13 | Determine business continuity strategies and solutions | BC Manager,Top Mgt,CIO | 4399600% | 3 | 4399900% | 2 | 66.67%
14 | Establish business continuity plans | BC Manager,Business Reps,CIO | 4399700% | 5 | 4400100% | 2 | 40%
15 | Plan business continuity exercising and testing | BC Manager,CIO,Top Mgt | 4399800% | 8 | 4400700% | 6 | 75%
16 | Document communications procedures | BC Manager,Business Reps | 4399900% | 1 | 4399900% | 0 | 0%
17 | Define approach to monitoring, measurement, analysis and evaluation | BC Manager,Top Mgt | 4400000% | 1 | 4400000% | 1 | 100%
18 | Awareness training | BC Manager,Business Reps | 4400100% | 1 | 4400100% | 0 | 0%
19 | Establish continual improvement process | BC Manager,Top Mgt | 4400200% | 2 | 4400500% | 1 | 50%
20 | Internal audit | BC Manager,Business Reps,CIO,Internal Audit Team | 4400300% | 6 | 4401100% | 3 | 50%
21 | Perform management review | BC Manager,Top Mgt | 4400400% | 5 | 4400800% | 0 | 0%
22 | Certification stage one | BC Manager,Top Mgt,External Auditor | 4400500% | 8 | 4401400% | 0 | 0%
23 | Certification stage two | BC Manager,Business Reps,External Auditor,Top Mgt | 4400600% | 1 | 4400600% | 0 | 0%
24 | Post Project Review | Project Mgr,BC Manager,Top Mgt | 4400700% | 2 | 4400800% | 0 | 0%
Grand Total

## Project Dashboard
Project Dashboard
To refresh chart data, click on “Refresh All” on the Data ribbon.
Project timeline: | 2-June-2020 to 2-July-2020
Project tasks and progress
Project budget overview
24

## Tasks & Progress Pivots (hidden)
Project tasks and progress
Count of REF | Task Status | Task Progress | Project Days |  | Project Days | %
24 | Not Started | 6 | Completed Work Days | 37 | Days Completed | 33.04%
| In Progress | 14 | Total Work Days | 112 | Days Remaining | 66.96%
| Completed | 4
| Remaining | 20
| Total Tasks | 24
| Task Status | Sum of Task Progress
| Total Tasks | 24
| Completed | 4
| Remaining | 20
| Not Started | 6
| In Progress | 14

## Budget Pivots (hidden)
Project budget overview
ITEM | Budget | Spent to date | Budget remaining | Values
Certification auditing | 500 | 0 | 500 | Spent to date | 8650
Communication | 1200 | 600 | 600 | Budget remaining | 10550
External Consultancy | 2000 | 1000 | 1000 | Budget | 19200
Hardware | 3000 | 2000 | 1000
Internal auditing | 500 | 250 | 250
Internal resources | 5000 | 1500 | 3500
Offices and furniture | 1000 | 1000 | 0
Professional memberships | 500 | 0 | 500
Software tools | 2500 | 1200 | 1300
Training | 1500 | 500 | 1000
Travel and subsistence | 1500 | 600 | 900
Grand Total | 19200 | 8650 | 10550

## Scroll Bar (hidden)
Scroll Bar
Scroll Bar
0