Business Continuity Test Plan

ISO22301 Toolkit: Version 6
©CertiKit

Implementation guidance

The header page and this section, up to and including Disclaimer, must be removed from the final version of the document. For more details on replacing the logo, yellow highlighted text and certain generic terms, see the Completion Instructions document.

Purpose of this document

This document sets out how a specific individual business continuity test will be carried out.

Areas of the standard addressed

This document is relevant to requirements in the following sections of the ISO22301 standard:

8. Operation

  - 8.5 Exercise programme

General guidance

This document will be one of a number that are created during the year to plan individual tests according to the overall testing schedule that is defined in the Business Continuity Exercise Programme.

It will be important to be clear about what the test is intended to achieve and how that relates to the overall set of business continuity plans. The test can take various forms including a desktop review, walk-through or full plan test (where alternative locations and facilities may be used).

Once the test has been completed the standard requires a post-exercise report to be produced.

Review frequency

We would recommend that this document is reviewed and approved prior to the test being carried out. The format and contents of the document should be reviewed at least annually and ideally after each test to keep it as current as possible.

Document fields

This document may contain fields which need to be updated with your own information, including a field for Organization Name that is linked to the custom document property “Organization Name”.

To update this field (and any others that may exist in this document):

- Update the custom document property “Organization Name” by clicking File > Info > Properties > Advanced Properties > Custom > Organization Name.

- Press Ctrl A on the keyboard to select all text in the document (or use Select, Select All via the Editing header on the Home tab).

- Press F9 on the keyboard to update all fields.

- When prompted, choose the option to just update TOC page numbers.

If you wish to permanently convert the fields in this document to text, for instance, so that they are no longer updateable, you will need to click into each occurrence of the field and press Ctrl Shift F9.

If you would like to make all fields in the document visible, go to File > Options > Advanced > Show document content > Field shading and set this to “Always”. This can be useful to check you have updated all fields correctly.

Further detail on the above procedure can be found in the toolkit Completion Instructions. This document also contains guidance on working with the toolkit documents with an Apple Mac, and in Google Docs/Sheets.

Copyright notice

Except for any specifically identified third-party works included, this document has been authored by CertiKit, and is ©CertiKit except as stated below. CertiKit is a company registered in England and Wales with company number 6432088.

Licence terms

This document is licensed on and subject to the standard licence terms of CertiKit, available on request, or by download from our website. All other rights are reserved.  Unless you have purchased this product you only have an evaluation licence.

If this product was purchased, a full licence is granted to the person identified as the licensee in the relevant purchase order. The standard licence terms include special terms relating to any third-party copyright included in this document.

Disclaimer

Please Note: Your use of and reliance on this document template is at your sole risk. Document templates are intended to be used as a starting point only from which you will create your own document and to which you will apply all reasonable quality checks before use.

Therefore, please note that it is your responsibility to ensure that the content of any document you create that is based on our templates is correct and appropriate for your needs and complies with relevant laws in your country.

You should take all reasonable and proper legal and other professional advice before using this document.

CertiKit makes no claims, promises, or guarantees about the accuracy, completeness or adequacy of our document templates; assumes no duty of care to any person with respect its document templates or their contents; and expressly excludes and disclaims liability for any cost, expense, loss or damage suffered or incurred in reliance on our document templates, or in expectation of our document templates meeting your needs, including (without limitation) as a result of misstatements, errors and omissions in their contents.

Business Continuity Test Plan

| DOCUMENT REF | BCMS-DOC-08-10 |
| --- | --- |
| VERSION | 1 |
| DATED | [Insert date] |
| DOCUMENT AUTHOR | [Insert name] |
| DOCUMENT OWNER | [Insert name/role] |

Revision history

| VERSION | DATE | REVISION AUTHOR | SUMMARY OF CHANGES |
| --- | --- | --- | --- |

Distribution

| NAME | TITLE |
| --- | --- |

Approval

| NAME | POSITION | SIGNATURE | DATE |
| --- | --- | --- | --- |

Contents

1	Introduction	8

2	Test scope and objectives	9

2.1	Overview	9

2.2	Plan(s) to be tested	9

2.3	Test objectives	9

3	Test plan	10

3.1	Date and location	10

3.2	Resources required	10

3.2.1	People	10

3.2.2	IT Systems	11

3.2.3	Facilities	11

3.2.4	Supplier and partner staff	11

3.3	Items to be taken to the test	11

3.4	Test timing	12

3.5	Review and follow-up	12

Tables

Table 1: Plan(s) to be tested	9

Table 2: Test objectives	9

Table 3: People involved in the test	10

Table 4: IT systems required	11

Table 5: Test timing	12

# Introduction

[Organization Name] has invested a significant amount of time and resources in creating a Business Continuity Management System (BCMS) and resulting plans in accordance with the requirements of the ISO22301 international standard for business continuity.

The purpose of the BCMS is to protect the critical business activities of the organization by lessening the risk of a disruptive incident and by being prepared to manage such an incident in a controlled way.

There is a need to ensure that the plans in place are workable and can be implemented in an emergency situation. Beyond learning the lessons of real incidents that have taken place, the only way to ensure this is to carry out an appropriate programme of testing. Such a programme is defined in the related document Business Continuity Exercise Programme which sets out the types and calendar schedule for testing.

The purpose of this document is to plan the necessary activities to test one or more specific aspects of business continuity plans as defined in the agreed schedule.

# Test scope and objectives

## Overview

This will be a full test to determine the adequacy of the current plan to recover Service 1 in the event of 40% or more of staff becoming unavailable due to a flu pandemic or other unexpected cause.

Only top management and team leaders will be aware of the test beforehand due to the need to test the speed of reaction achievable. Qualified staff will be available to ensure that customer service is not impacted.

## Plan(s) to be tested

The following business continuity plan(s) will be tested as part of this exercise:

| PLAN REF | PLAN TITLE | PLAN VERSION | RISK(S) ADDRESSED | TYPE OF TEST |
| --- | --- | --- | --- | --- |
| Plan 12 | Staff Unavailable to support Service 1 | 1.0 | Flu pandemic | Full test |

Table 1: Plan(s) to be tested

## Test objectives

The objectives of testing the plan identified are:

| REF | OBJECTIVE | MEASUREMENT METHOD | TARGET |
| --- | --- | --- | --- |
| 1. | To assess the level of skill available from replacement staff drafted in to support the service | Customer feedback; Assessment of qualified staff | Basic to moderate |
| 2. | To assess number of replacement staff available at short notice | Number of staff | In line with plan |
| 3. | To test whether communication procedures are adequate | % replacement staff reached within 12 hours | 80% |
| 4. | To determine whether all required facilities are available to replacement staff | List of facilities successfully accessed and those required but not available | All required facilities available |

Table 2: Test objectives

# Test plan

## Date and location

The test will take place on Wednesday 12th October 20xx at the main location from which Service 1 is provided. Everyone involved will meet in the conference room at 09:00.

## Resources required

The following resources will be needed to allow the test to run smoothly.

### People

The following members of staff will be involved in the test with the role specified:

| NAME | TITLE | ROLE IN TEST |
| --- | --- | --- |
| Person A | Business Continuity Manager | Test Co-ordination |
| Person B | Quality Auditor | Internal audit |
| Person C | Team Leader | Observer |
| Person D | Team Member | Observer |
| Person E | Team Member | Observer |
| Person F | Team Member | Observer |
| Person G | Team Member | Observer |
| Person H | Team Member | Observer |
| Person I | Team Member | Observer |
| Person J | Team Member | Observer |
| Person K | Account Administrator | Replacement team member |
| Person L | Buying Clerk | Replacement team member |
| Person M | Receptionist | Replacement team member |
| Person N | Warehouse Clerk | Replacement team member |
| Person O | Driver | Replacement team member |

Table 3: People involved in the test

### IT Systems

Access to the following IT systems will be required:

| IT SYSTEM | TYPE OF ACCESS | COMMENTS |
| --- | --- | --- |
| Email | Mobile |  |
| Shared drive | Full |  |

Table 4: IT systems required

### Facilities

The following facilities will be required on the day of the test:

Large meeting room

Projector

Flip chart

Network access

Printer

These will be booked by the Business Continuity Manager in advance of the test.

### Supplier and partner staff

The following people will be required from external third parties during the test:

Specify any support needed from third parties

## Items to be taken to the test

The following items will need to be taken to the test site:

Business continuity plan

Uniforms and other clothing

Safety equipment

The BC Manager will allocate responsibility for obtaining and transporting these items on the day of the test.

## Test timing

The approximate schedule of the test will be as follows:

| TIME | STEP | WHO | COMMENTS |
| --- | --- | --- | --- |
| 09:00 | Brief the team that a test will be carried out today | BC Manager | Supported by Team Leader |
| 10:00 | Begin contacting replacement staff | BC Manager |  |
| 11:00 | Brief replacement staff | BC Manager | Supported by Team Leader |
| 12:00 | Begin providing service using replacement staff | Replacement staff | Observed by qualified staff |
| 17:00 | Review meeting | All |  |
| 18:00 | End of test |  |  |

Table 5: Test timing

## Review and follow-up

All aspects of the test will be documented, and a post-exercise review carried out to assess whether the test was successful against its objectives. Any recommendations or deficiencies will be managed through to completion and tracked as part of the management review process.