## Assessment Details
Assessment Details
Assessment Title | Assessment of business operations at the Chicago facility
Assessment Scope | All business processes, equipment and personnel involved in the creation of physical products from Chicago.
Context of Assessment | Increased demand for product means that production in Chicago is key to the success of the company. Concerns over manufacturing equipment malfunctions have also been raised.
Risk Acceptance Criteria | Risks classified as Low risk level will be accepted.
Version | 1
Dated | 12 May 20xx
Assessors | A.N. Other
Assessment Participants | COO Chicago, VP Production.
Approval | CEO
Date Approved | 24 May 20xx
Risk and Opportunity Assessment and Treatment Tool
BCMS-FORM-08-2

## Risk Assessment
Business Continuity Risk Assessment and Treatment Tool
Start with the risks that are felt to have the highest likelihood and impact combination.
To refresh chart data on the risk dashboard, click on “Refresh All” on the Data ribbon.
RISK DESCRIPTION |  |  |  | PRE-TREATMENT ASSESSMENT | [6 empty] | TREATMENT PLAN |  |  |  |  | POST-TREATMENT ASSESSMENT
Ref | Risk Summary | Risk Description | Risk Owner | Existing Controls | Likelihood | Likelihood Rationale | Impact | Impact Rationale | Risk Score | Risk Level | Treatment Option Chosen | Proposed Treatment Action | Treatment Cost | Treatment Action Owner | Treatment Action Timescale | Post-Treatment Likelihood | Post-Treatment Likelihood Rationale | Post- Treatment Impact | Post-Treatment Impact Rationale | Post-Treatment Risk Score | Post-Treatment Risk Level | Comments
1 | Loss of power to plant | Electrical supply to the facility ceases suddenly for unknown and possibly extended period | Facilities Manager | Facility is fed by two separate sub-stations. A generator capable of supporting the plant is installed and tested regularly | 2 | Power has failed twice in the last five years, each time for more than two days | 2 | It has been proven that the facility can operate successfully during a power failure | 4 | LOW | Accept |  | 0 |  |  | 2 |  | 2 |  | 4 | LOW
2 | Hazardous materials incident in surrounding area | Emergency is declared on industrial park due to an incident with hazardous materials being handled by a company with premises there | Facilities Manager | None | 3 | There is known to be an increased use of such materials locally | 4 | An incident may mean that the plant must be shut down for an extended period | 12 | HIGH | Modify | Create plan to move production to an alternate facility within 1 week of incident | 25000 | Facilities Manager | 6 months | 3 | No change to likelihood | 3 | Loss of production would be limited to one week | 9 | MEDIUM
3 | Fire in plant | Significant fire destroys major parts of the facility, rendering it inoperable | Facilities Manager | Smoke detectors, automatic fire suppression system, 24x7 security | 2 | Few sources of ignition for accidental fire; arson is a possibility | 4 | Fire would affect the ability of the facility to produce | 8 | MEDIUM | Modify | Create plan to move production to an alternate facility within 1 week of incident | 25000 | Facilities Manager | 6 months | 2 | No change to likelihood | 3 | Loss of production would be limited to one week | 6 | MEDIUM
4 | Critical equipment failure | Machinery essential for the manufacturing process fails and cannot be repaired in a timely fashion | Operations Manager | Maintenance contract in place | 4 | Some key machines are old and prone to failure; parts are hard to obtain | 4 | Production would stop if key machinery failed | 16 | HIGH | Modify | Create proposal to replace key machinery as soon as possible | 10000 | Maintenance Engineer | 3 months | 2 | New machinery will be less likely to fail | 4 | Impact remains the same | 8 | MEDIUM
5 | Loss of key staff | Workers critical to the production process are unable or unwilling to attend site | Operations Manager | Cross-training means that most jobs can be done by most people | 2 | Health record of staff is historically good and there have been no problems with employee relations in the last 5 years | 2 | Much of process is automated and replacement staff can be found easily | 4 | LOW | Accept |  |  |  |  | 2 |  | 2 |  | 4 | LOW
6 | Critical IT systems failure | IT systems supporting the production process are rendered inoperable by hardware, software or infrastructure failure | IT Manager | Redundant systems are in place | 3 | Systems have been hit by hacking attempts and viruses recently | 3 | Production can run without IT systems, but reporting is affected | 9 | MEDIUM | Modify | Install additional firewall. Increase security awareness training for employees | 8000 | IT Manager | 2 months | 2 | Hacking will be more difficult and fewer viruses will be introduced | 3 | No change to impact | 6 | MEDIUM
7 | Flooding | The site is subject to extensive and extended flooding | Facilities Manager | None | 1 | No natural or man-made water sources in the area | 4 | Production would cease until flooding subsided | 4 | LOW | Accept |  |  |  |  | 1 |  | 4 |  | 4 | LOW
8 | Global pandemic | A situation similar to the COVID-19 pandemic occurs, with very widespread impact on health and business. | Operations Manager | Cross-training means that most jobs can be done by most people | 3 | It has happened before, although it was labelled a one in a century event. | 5 | Very significant impact on revenue and production. | 15 | HIGH | Modify | Maintain stocks of PPE, increase online presence | 100000 | Operations Manager | 12 months | 3 | No change to likelihood | 4 | There would still be a significant financial impact | 12 | HIGH
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on B13: This section describes the nature of the risk and the risk owner.
Note on F13: This is an assessment of the level of current risk, taking into account any controls already in place to address it.
Note on M13: For those risks that are not accepted, a plan must be in place to take action to address the risk.
Note on R13: This section is used to assess what the level of risk will be, once the treatment actions have been carried out.
Note on B14: Enter a reference number here.
Note on C14: A short name that the risk will be known by.
Note on D14: Record the risk with as full a description as possible.
Note on E14: Name of the person responsible for the risk.
Note on F14: Existing controls which could lessen the risk likelihood and/or impact.
Note on G14: Select a score from 1 to 5, where 1 is a low likelihood and 5 is high.
Note on H14: Reasoning for giving that likelihood score.
Note on I14: Select a score from 1 to 5, where 1 is low impact and 5 is high.
Note on J14: Brief explanation of why the impact score was assigned.
Note on K14: Risk score of between 1 and 25. This field will be automatically generated.
Note on L14: Risk level of low, medium or high, depending on the risk score. This field will be automatically generated.
Note on M14: Select a risk treatment option from the drop-down menu.
Note on N14: Record any proposed actions intended to address the risk.
Note on O14: How much money will the proposed treatment action cost?
Note on P14: The person or role tasked with completing the treatment action.
Note on Q14: The date or timeframe by which the treatment action must be completed.
Note on R14: Select a score from 1 to 5, where 1 is a low likelihood and 5 is high.
Note on S14: Reasoning for giving that likelihood score.
Note on T14: Select a score from 1 to 5, where 1 is low impact and 5 is high.
Note on U14: Reasoning for giving that impact score.
Note on V14: Risk score of between 1 and 25. This field will be automatically generated.
Note on W14: Risk level of low, medium or high, depending on the risk score. This field will be automatically generated.
Note on X14: Enter any other comments here.

## Opportunity Assessment
Opportunity Assessment and Action Planning Tool
This is an assessment of the opportunities that may occur and what could be done to capitalize on them. Opportunities are uncertainties that are likely to have a positive effect (unlike risks, which are likely to have a negative effect).
To refresh chart data on the risk dashboard, click on “Refresh All” on the Data ribbon.
REF | OPP SUMMARY | OPP DESCRIPTION | OPP TYPE | OPP OWNER | LIKELIHOOD | LIKELIHOOD RATIONALE | IMPACT | IMPACT RATIONALE | OPP SCORE | OPP LEVEL | ACTION | ACTION OWNER | ACTION TIMESCALE | COMMENTS
1 | Increase in funding for business continuity | Possibly due to an internal or external event, more money is made available to address business continuity within the organization. | Financial | BC Manager | 3 | The expectation of a major event within our industry is high. | 1 | Several control areas are currently underfunded and would benefit from more money. | 3 | LOW | Obtain quotes and costings for additional controls e.g. software that would have a beneficial effect on business continuity if purchased. This will allow us to move quickly if this opportunity occurs. | BC Manager | 3 months
2 | Better AI improves failure detection and prevention | Advances in Artificial Intelligence may make mechanical failures less likely. | Technical | Operations Manager | 4 | The pace of change in AI has accelerated recently. | 4 | One of our biggest problems is determining when a machine is likely to fail. | 16 | HIGH | Subscribe to vendor's newsletters; attend industry events. | Operations Manager | 1 month
3 | Merger or Acquisition | Our organization merges with another that has newer infrastructure and is less prone to failures. | Organizational | COO | 3 | Several deals are rumoured to be under discussion. | 3 | There may be better access to tools and skills. | 9 | MEDIUM | Perform an early assessment of any potential mergers to identify potential benefits. | COO | 2 weeks
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on B12: Enter a reference number here.
Note on C12: A short name that the opportunity will be known by.
Note on D12: Record the opportunity with as full a description as possible.
Note on E12: Examples types could be Financial, Technical, Resources, Reciprocal Arrangement, but any useful classification may be used.
Note on F12: Name of the person responsible for the opportunity.
Note on G12: Select a score from 1 to 5, where 1 is a low likelihood and 5 is high.
Note on H12: Reasoning for giving that likelihood score.
Note on I12: Select a score from 1 to 5, where 1 is low impact and 5 is high.
Note on J12: Brief explanation of why the impact score was assigned.
Note on K12: Opportunity score of between 1 and 25. This field will be automatically generated.
Note on L12: Opportunity level of low, medium or high, depending on the risk score. This field will be automatically generated.
Note on M12: Record any actions proposed to take advantage of the opportunity.
Note on N12: Who is responsible for performing the identified actions.
Note on O12: When the identified actions should be completed by.
Note on P12: Any additional relevant information.

## Dashboard
Business Continuity risk assessment and opportunity dashboard
To refresh chart data on the risk dashboard, click on “Refresh All” on the Data ribbon.
Pre-treatment assessment
Post-treatment assessment
Classification of risk and opportunity level | [7 empty] | Risk profile diagram
The chart below shows the rating scheme used to determine risk and opportunity level based on a combination of likelihood and impact. | [7 empty] | The charts below show the spread of risk severities before and after risk treatment.
LIKELIHOOD: What are the chances of the risk/opportunity event happening?
| IMPACT: How major could the consequences be if the risk/opportunity event happened? | [6 empty] | Pre-treatment | [6 empty] | Post-treatment
|  | INSIGNIFICANT 1 | MINOR 2 | SIGNIFICANT 3 | MAJOR 4 | SEVERE 5 | Risk Likelihood | 5 | 0 | 0 | 0 | 0 | 0 | Risk Likelihood | 5 | 0 | 0 | 0 | 0 | 0
| ALMOST CERTAIN 5 | MEDIUM 5 | MEDIUM 10 | HIGH 15 | HIGH 20 | HIGH 25 |  | 4 | 0 | 0 | 0 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 0
| LIKELY 4 | LOW 4 | MEDIUM 8 | HIGH 12 | HIGH 16 | HIGH 20 |  | 3 | 0 | 0 | 1 | 1 | 1 |  | 3 | 0 | 0 | 1 | 1 | 0
| MODERATE 3 | LOW 3 | MEDIUM 6 | MEDIUM 9 | HIGH 12 | HIGH 15 |  | 2 | 0 | 2 | 0 | 1 | 0 |  | 2 | 0 | 2 | 2 | 1 | 0
| UNLIKELY 2 | LOW 2 | LOW 4 | MEDIUM 6 | MEDIUM 8 | MEDIUM 10 |  | 1 | 0 | 0 | 0 | 1 | 0 |  | 1 | 0 | 0 | 0 | 1 | 0
| RARE 1 | LOW 1 | LOW 2 | LOW 3 | LOW 4 | MEDIUM 5 |  |  | 1 | 2 | 3 | 4 | 5 |  |  | 1 | 2 | 3 | 4 | 5
[7 empty] | Risk impact | [6 empty] | Risk impact
Treatment plan
Opportunity assessment

## Pre-treatment Risks Pivot (hidden)
Number of Pre-treatment risks by risk level
Risk level | Pre-treatment
Low | 3
Medium | 2
High | 3
Risk level | Pre-treatment
Low | 3
Medium | 2
High | 3

## Pre-treatment Risk Owners Pivot (hidden)
Pre-treatment risk levels by risk owner
Risk Level | Risk Owner | Count of Risk Level
LOW | Facilities Manager | 2
| Operations Manager | 1
MEDIUM | IT Manager | 1
| Facilities Manager | 1
HIGH | Facilities Manager | 1
| Operations Manager | 2

## Post-treatment Risks Pivot (hidden)
Number of Post-mitigation risks by risk level
Risk level | Post-treatment
Low | 3
Medium | 4
High | 1
Risk level | Post-treatment
Low | 3
Medium | 4
High | 1

## Pre & Post Risks By Level Pivot (hidden)
Number of risks by risk level pre and post treatment
Risk level | Pre-treatment | Post-treatment
Low | 3 | 3
Medium | 2 | 4
High | 3 | 1
Risk level | Pre-treatment | Post-treatment
Low | 3 | 3
Medium | 2 | 4
High | 3 | 1

## Treatment option chosen Pivot (hidden)
Risks by treatment option chosen
Treatment Option Chosen | Count of Risk Summary
Accept | 3
Modify | 5

## Total treatment costs Pivot (hidden)
Total treatment cost by risk level
Risk Level | Sum of Treatment Cost
LOW | 0
MEDIUM | 33000
HIGH | 135000

## Treatment Action Owner (hidden)
Treatment action owner
Count of Treatment Action Owner | Risk Level
Treatment Action Owner | LOW | MEDIUM | HIGH
Facilities Manager |  | 1 | 1
IT Manager |  | 1
Maintenance Engineer |  |  | 1
Operations Manager |  |  | 1
(blank)

## Opps By Level (hidden)
Opportunities by level
OPP LEVEL | Count of OPP LEVEL
MEDIUM | 1
HIGH | 1
LOW | 1

## Opps By Level & Type (hidden)
Opportunities by level and type
OPP TYPE | OPP LEVEL | Count of REF
Financial | LOW | 1
Organizational | MEDIUM | 1
Technical | HIGH | 1

## Opp Levels By Opp Owner (hidden)
Opportunity levels by opportunity owner
OPP OWNER | OPP LEVEL | Count of OPP LEVEL
BC Manager | LOW | 1
COO | MEDIUM | 1
Operations Manager | HIGH | 1

## Opp Action Owner (hidden)
Opportunity action owner
ACTION OWNER | OPP LEVEL | Count of REF
BC Manager | LOW | 1
COO | MEDIUM | 1
Operations Manager | HIGH | 1

## Example Threats
Risk Assessment - Example Threats
The following is a standard list of typical threats that may be use as guidance for your risk assessment.
THREAT CATEGORY | THREAT | EXAMPLE
Human | Malicious outsider | Someone launches a denial of service attack on your cloud service platform
| Malicious insider | An employee or trusted third party accesses information in an unauthorised manner from inside your network
| Loss of key personnel | One or more people with key skills or knowledge are unavailable perhaps due to extended sickness
| Human error | An employee accidentally deletes customer data
| Accidental loss | A manager loses a memory stick with customer bank details on it
Natural | Fire | Your data centre burns down due to an electrical fault
| Flood | The nearby river breaks its banks and your main office is severely flooded
| Severe weather | Non-one can get into the office due to the weather
| Earthquake | The area of your main data centre is affected by an earth tremor that damages all your servers
| Lightning | All your servers are fried by a lightning strike on the data centre building
| Infection | A new strain of virus results in widespread lockdown of people's movements
Technical | Hardware failure | A key physical server has a processor failure
| Software failure | Your financial system processes invoices incorrectly due to a bug
| Virus/Malicious code | A virus spreads throughout your network preventing access to your (and your customers') data
Physical | Sabotage | A disgruntled ex-employee takes an axe to your server room
| Theft | You come in on Monday morning to find some important drives have been stolen
| Arson | Someone with a grudge against your organization starts a fire during the night
Environmental | Hazardous waste | A lorry carrying hazardous waste has an accident outside your office
| Power failure | The sub-station supplying your area has a meltdown
| Gas supply failure | There is a suspected leak and all supplies are turned off
Operational | Process error | Your new data transfer procedure doesn't cater for unexpected circumstances and PII is lost or sent to the wrong destination
| Crime scene | A crime happens in or near your office and the area is sealed off by police

## Likelihood
Risk or Opportunity Likelihood
This table should be used to decide upon the most appropriate likelihood for a particular risk or opportunity.
LIKELIHOOD | DESCRIPTION | SUMMARY
1 | Improbable | Has never happened before and there is no reason to think it is any more likely now
2 | Unlikely | There is a possibility that it could happen, but it probably won't
3 | Likely | On balance, the risk is more likely to happen than not
4 | Very Likely | It would be a surprise if the risk did not occur either based on past frequency or current circumstances
5 | Almost certain | Either already happens regularly or there is some reason to believe it is virtually imminent

## Risk Impact
Risk Impact
This table should be used as guidance to help to decide upon the correct impact rating for a particular risk.
IMPACT LEVEL |  | IMPACT AREAS
Impact rating | General description | Impact on product or service quality | Impact on financial viability | Impact on staff or public well-being | Damage to reputation | Impact of breaching legal or regulatory requirements | Environmental damage
1 | Negligible | No effect | Very little or none | Very small additional risk | No adverse comment | No implications | Negligible
2 | Slight | Some local disturbance to normal business operations | Some | Within acceptable limits | Localised discontent | Small risk of not meeting compliance | Small, very local impact that can be managed and corrected
3 | Moderate | Can still deliver product/service with some difficulty | Unwelcome but could be borne | Elevated risk requiring immediate attention | Some internal and external criticism | In definite danger of operating illegally | Impact restricted geographically and can be corrected quickly
4 | High | Business is crippled in key areas | Severe effect on income and/or profit | Significant danger to life | A severe test of customer loyalty | Operating illegally in some areas | Geographically wide impact area with a degree of clean-up possible over time
5 | Very High | Out of business; no service to customers | Crippling; the organization will go out of business | Real or strong potential loss of life | Trust in organization is irreparably damaged | Severe fines and possible imprisonment of staff | Catastrophic impact affecting the environment badly over a wide area

## Opportunity Impact
Opportunity Impact
This table should be used as guidance to help to decide upon the correct impact rating for a particular opportunity.
IMPACT LEVEL |  | EXAMPLE IMPACT AREAS
Impact rating | General description | Impact on product or service quality | Impact on financial performance | Impact on staff or public well-being | Impact on reputation | Impact on compliance with legal or regulatory requirements | Environmental impact
1 | Negligible | No effect | Very little or none | Very small additional benefit | No positive comment | No implications | Negligible
2 | Slight | Some local improvement to normal business operations | Small increase in revenue or profitability | Minor benefit to a few individuals | Localised improvement on a small scale | Small improvement in meeting compliance requirements | Small, very local positive impact
3 | Moderate | Temporary significant improvement or fair permanent change | Reasonable increase in profit, revenue or other business metric | Good improvement across a limited audience | Some internal and external praise and positive attention | Compliance is improved across a number of areas | Positive impact restricted geographically
4 | High | product or service performance is significantly boosted in key areas | Very significant increase in profit or business performance | Major improvement to health and quality of life to a wide audience | Major reputational improvement | Level of compliance becomes very significant and/or more easily attained | Geographically wide impact area with permanent improvement over time
5 | Very High | Huge improvement in existing or new products or services | Complete transformation in business performance on a permanent basis | Transformation of health and quality of life for a very large group of people | The organization is seen as an industry leader in its sector | Very large change in compliance levels with significant benefits | Huge benefit to the environment on a wide scale

## Selection Tables (hidden)
Selection Tables
ONE TO FIVE | TREATMENT OPTIONS
Select… | Select…
1 | Accept
2 | Avoid
3 | Modify
4 | Share
5