Business Continuity Test Report

Business Continuity Test Report

| DOCUMENT REF | BCMS-REP-01-1 |
| --- | --- |
| VERSION | 1 |
| DATED | 08 September 2021 |
| DOCUMENT AUTHOR | Herbert Morse |
| DOCUMENT OWNER | Herbert Morse |

Revision history

| VERSION | DATE | REVISION AUTHOR | SUMMARY OF CHANGES |
| --- | --- | --- | --- |
| 1 | 5.2.20xx | Herbert Morse | New document |

Distribution

| NAME | TITLE |
| --- | --- |
| Jeremy Gibbs | Managing Director |
| Herbert Morse | Business Continuity Manager |
| Peter Calling | IT Manager |

Approval

| NAME | POSITION | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Jeremy Gibbs | Managing Director |  | 12th April 20xx |

Contents

1	Introduction	4

2	Test scope and objectives	5

2.1	Overview	5

2.2	Plan(s) tested	5

3	Test report	6

3.1	Date and location	6

3.2	Resources used	6

3.2.1	People	6

3.2.2	IT Systems	7

3.2.3	Facilities	7

3.2.4	Supplier and partner staff	7

3.3	Items taken to the test	7

3.4	Sequence of events	8

4	Success against objectives	9

5	Lessons learned	10

6	Conclusion	11

Tables

Table 1: Plan(s) tested	5

Table 2: People involved in test	6

Table 3: IT systems required	7

Table 4: Sequence of events	8

Table 5: Success against objectives	9

Table 6: Lessons learned	10

# Introduction

Stanmer Ltd has invested a significant amount of time and resources in creating a Business Continuity Management System (BCMS) and resulting plans and procedures in accordance with the requirements of the ISO22301 international standard for business continuity.

The purpose of the BCMS is to protect the critical business activities of the organization by lessening the risk of a disruptive incident and by being prepared to manage such an incident in a controlled way.

There is a need to ensure that the plans in place are workable and can be implemented in an emergency situation. Beyond learning the lessons of real incidents that have taken place, the only way to ensure this is to carry out an appropriate programme of testing. Such a programme is defined in the related document Business Continuity Exercise Programme which sets out the types and calendar schedule for testing.

The purpose of this document is to document the results of a test that has been carried out of a specific aspect of a business continuity plan as defined in the agreed schedule.

# Test scope and objectives

## Overview

This was a full test to determine the adequacy of the current business continuity procedure to recover from a loss of mains electrical services across the administration support department.

Only top management and team leaders were made aware of the test beforehand due to the need to test the speed of reaction achievable. Qualified staff were available to ensure that customer service was not impacted.

## Plan(s) tested

The following business continuity procedures(s) was tested as part of this exercise:

| PLAN REF | PLAN TITLE | PLAN VERSION | RISK(S) ADDRESSED | TYPE OF TEST |
| --- | --- | --- | --- | --- |
| BCMS-DOC-08-27 | Loss vital main services | 1.0 | Loss of main electrical supply across the administration support department | Full test |
| BCMS-COP-07-15 | IT Emergency provision for loss of mains power | 2.0 | Loss of IT systems due to break in main electrical supply | Partial test |

Table 1: Plan(s) tested

# Test report

## Date and location

The test took place on Wednesday 8th April 20xx at the main location from which administration support is provided to all business units. Everyone involved met in the conference room at 08:30.

## Resources used

The following resources were used as part of the test.

### People

The following members of staff were involved in the test with the role specified:

| NAME | TITLE | ROLE IN TEST |
| --- | --- | --- |
| Herbert Morse | Business Continuity Manager | Test Co-ordination |
| Simon Piper | Quality Auditor | Internal audit |
| Marion Potts | Operations Manager | Observer |
| Raj Singh | Assistant Production Manager | Observer |
| Richard Pol | Warehouse Supervisor | Observer |
| Tracy Edwards | Compliance Officer | Observer |
| Lee Jung | Facility Officer | Observer |
| Tony Young | Transport Officer | Replacement team member |
| Stephen Noor | Transport Officer | Replacement team member |
| Mark Hotts | Warehouse Operator | Replacement team member |
| Tasmin Youta | Production Operator | Replacement team member |
| Alan Darbridge | Driver | Replacement team member |

Table 2: People involved in test

### IT Systems

Access to the following IT systems was required:

| IT SYSTEM | TYPE OF ACCESS | COMMENTS |
| --- | --- | --- |
| Email | Mobile | Alternative contact information |
| Shared drive | Full | Potential loss of data |
| Emergency UPS system | Full | Potential damage to equipment |

Table 3: IT systems required

### Facilities

The following facilities were provided on the day of the test:

Large meeting room

Projector

Flip chart

Network access

Printer

### Supplier and partner staff

The following people were involved from external third parties during the test:

N/A

## Items taken to the test

The following items were taken to the test site:

Business continuity plan

Uniforms and other clothing

Safety equipment

Documented procedures as stated in section 2.2

## Sequence of events

The approximate sequence of events of the test was as follows:

| TIME | STEP | WHO | COMMENTS |
| --- | --- | --- | --- |
| 08:30 | The team was briefed that a test would be carried out today | BC Manager | Started on time |
| 09:15 | Instigated simulated loss of electrical mains power | Facilities Manager | Observers in support administration department informed all staff that power was lost |
| 09:15 | Informed IT department of loss of electrical mains power | Operations Manager | Good reaction by IT team although a little confused at the start |
| 09:30 | Observed actions of both support administration department and IT department | Observers | Some support staff were observed to continue to use their PCs |
| 14:45 | Informed IT department main electrical supply had been restored | Operations Manager | Good response by IT team |
| 16:00 | Review meeting | All | Good level of feedback from all parties |
| 17300 | End of test |  |  |

Table 4: Sequence of events

# Success against objectives

The objectives of testing the plan identified prior to the test are set out below together with an assessment of whether they were achieved:

| REF | OBJECTIVE | MEASUREMENT METHOD | TARGET | OBJECTIVE | COMMENTS |
| --- | --- | --- | --- | --- | --- |
| 1. | To assess the level of knowledge of administration support staff and IT department to react to and recover from a loss of mains electrical supply | Observation by test staff using documented business continuity procedures | Moderate to good | Partially Achieved | Administration support department staff initially did not take the test seriously enough as some were observed continuing to use equipment they were told was not to be used. IT department reaction was good after a bit of a confused start. Once into the test, they acted well as a team. |
| 2. | To assess if business continuity procedures were followed and adequate | Observation by test staff using documented business continuity procedures and noting nonconformities | In line with plan | Achieved | IT team and Facilities team worked well together quickly identifying the necessary documents to use and followed the procedures |
| 3. | To test whether communication procedures are adequate | Observation by test staff using documented business continuity procedures | 90% | Achieved | All necessary communications as documented within the procedures were followed fully. Unfortunately, the administration support staff failed to report loss of computers to IT department for 25 minutes, hence the 90% mark |
| 4. | To determine whether all required facilities are in place to support administration support department | List of facilities successfully accessed, and emergency generator started prior to restarting systems and equipment | All required facilities available | Achieved | In general, the right facilities were available, however, the lack of knowledge by the administration support staff in closing down desktop and laptop computers could have resulted in potential loss of data and damage to the equipment |

Table 5: Success against objectives

# Lessons learned

The following lessons were learned as a result of this exercise. Recommendations to address the lessons are also given and will be actioned as part of continual improvement.

| REF | LESSON LEARNED | RECOMMENDATION | PERSON RESPONSIBLE | TIMESCALE |
| --- | --- | --- | --- | --- |
| 1. | The simulated power outage was not fully observed by the administration support staff | Firmer instruction by the observer during tests to staff during testing | BC Manager | One month |
| 2. | Need for a Work Instruction at the emergency generator to prevent wrong starting order | All members of the Facilities Team should be instructed on started emergency equipment | Facilities Manager | Two months |
| 3. | Review of inter department dependencies so business continuity procedures can be updated | Departments to review and identify all inter- department dependencies and inform BC Manager | BC Manager | Three months |
| 4. | Better management commitment to the testing process is needed for future tests to be successful | Top management to emphasise the need for effective business continuity testing to the management team | Top management | Two months |

Table 6: Lessons learned

# Conclusion

This was the third test to be carried out since the introduction of the Business Continuity Management System and as such it has added significantly to our knowledge in a number of important areas, especially with inter-department dependencies.

Further tests will be carried to further develop our procedures and recovery capabilities in line with the Business Continuity Exercise Programme.