## Action Log
REF | DATE RAISED | SOURCE | NONCONFORMITY DESCRIPTION | REACTIVE ACTION | CAUSE OF NON- CONFORMITY | IMPACT ASSESSMENT | CORRECTIVE ACTION | TIMESCALE | OWNER | PROGRESS (INC DATES) | STATUS | DATE CLOSED | EFFECTIVENESS REVIEW DATE | EFFECTIVENESS REVIEW RESULTS
1 | 26/11/20xx | Internal audit | Business continuity training has not been received by key people | Confirm training requirements and discuss availability for training with relevant people | Lack of engagement with HR | Business continuity plans may not be implemented correctly or updated promptly | Ensure that all new starters with BC responsibilities receive initial training and that longer term needs are identified | 6 months | BCM |  | Open
2 | 13/01/20xx | External audit | Insufficient top management involvement in reviews | Discuss the need for top management to be involved with the CFO | Lack of profile amongst top management | The effectiveness of the BCMS may be affected over time | Engage more fully with top management; request attendance at reviews | 3 months | BCM | 28/01/20xx - CFO has agreed that CTO and COO will attend next management review | Review Pending | 28/01/20xx
3 | 26/02/20xx | Supplier meeting | Supplier meetings are not being minuted | Create minutes from the last meeting based on notes | Some supplier managers were unaware of the requirement | Five of the last twelve meetings with suppliers have not been minuted | Inform supplier managers of the need to minute meetings | 1 month | BCM | 13/03/20xx - all supplier managers have now been informed of the need to minute meetings and received basic instruction on how to do so. | Closed | 13/03/20xx | 14/04/20xx | All supplier meetings in the last four weeks have been minuted to a good standard.
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
Nonconformity and Corrective Action Log BCMS-FORM-10-1
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on B10: Reference number. 1, 2, 3 etc.
Note on C10: Date nonconformity was raised.
Note on D10: Source from which nonconformity arose.
Note on E10: Description of nonconformity - what has gone wrong?
Note on F10: Initial action taken on discovering the nonconformity. For example, if the nonconformity involves insufficient top management involvement in reviews, discuss the need for more involvement with the CEO.
Note on G10: What was the cause of the nonconformity? What led to it occurring?
Note on H10: The impact of the nonconformity - what problems does it cause?
Note on I10: What needs to happen to ensure the problem is solved and doesn't happen again?
Note on J10: When will the nonconformity be addressed by?
Note on K10: Name or title of the employee responsible for putting measures in place to solve the nonconformity issue.
Note on L10: Add progress updates here.
Note on M10: Is the status of the nonconformity review pending, open or closed?
Note on N10: Date the nonconformity was closed (may be prior to a review).
Note on O10: Date of review to find out how successful the reactive and corrective actions have been since the nonconformity was closed.
Note on P10: Results of review. If the nonconformity has reoccurred, open a new nonconformity record.

## Data Tables
Data tables
Add or change the rows in the tables below to tailor the dropdown selections in the Action Log.
STATUS | COUNT
Open | 1
Closed | 1
Review Pending | 1
Total | 3

## Tables (hidden)
ONE TO FIVE
Select…
1
2
3
4
5