## Cover Page
Insert organization's logo here
Cybersecurity Risk Register
<organization name>
| Classification: | Choose Classification
| Version: | 1.0
| Date: | 2022-04-14

## Data Validation (hidden)
Please select a scope of risk | Please select a risk treatment | Choose Classification | 1 | Please select overall inherent risk rating | Please select a threat
IT assets | Risk Mitigation | Top Secret | 2 | Critical | Credential compromise
Business process | Risk Avoidance | Secret | 3 | High | Insider threats
Personnel | Risk Transfer | Confidential | 4 | Medium | Asset compromise
| Risk Acceptance | Public | 5 | Low | Social engineering
|  |  |  | Very Low | Data breach/leakage
|  |  |  | N/A | Loss of business continuity
Data loss
Mistaking compliance for protection
Regulatory fines
Outdated hardware
Vulnerable software
Cloud vulnerabilities
Ransomware
Malware
Attacks on IoT devices
Operational downtime
DDoS
Underestimation of risk occurrence probability
Partial risk assessment
Improper risk management
Improper incident response
Third party exposure

## Version control
Document Control
Classification
Choose Classification
Version control
Version | Date | Updated By | Version Details

## Risk register legend
Legend
Column name | Description
Risk identifier | Unique number assigned to Risk
Risk area (scope of risk) | Area in which the risk was identified
Risk owner | Head of organization or asset and process owner for which a risk was identified
Date of risk identification | Date of risk identification
Description of the risk | Risk description
Risk cause | Description of the cause of the inherent risk
Threat | Description of the threat arising from the risk
Risk analysis and consequences | Description of the possible consequences of the risk and information about the timescale in which they can happen.
Date of risk analysis and evaluation | Last date when risk has been identified and assessed
Inherent risk likelihood (1-5) | Quantitative evaluation of the inherent risk likelihood
Inherent risk magnitude/impact (1-5) | Quantitative evaluation of the inherent risk magnitude/impact
Overall inherent risk rating | Overall evaluation of the inherent risk (calculated automatically)
Is the overall inherent risk rated OK? If not please provide a reason | Information whether the risk owner accepts the risk evaluation or not and reason description in case of a mismatch
Updated overall inherent risk rating (manual override) | Overall evaluation of inherent risk and need for treatment actions provided manually by the risk owner in case of a mismatch
Type of treatment action | Type of treatment action chosen for the risk
Risk treatment description | Description of treatment actions which will be taken
Owner of the treatment action | Person responsible for implementing and monitoring of the treatment action
Deadline for action | Deadline for implementing the treatment action
Residual risk description | Residual risk description
Residual risk likelihood (1-5) | Quantitative evaluation of the residual risk likelihood
Residual risk magnitude/impact (1-5) | Quantitative evaluation of the residual risk magnitude/impact
Overall residual risk rating | Overall evaluation of the residual risk (calculated automatically)
Following steps description | Description of the steps which will follow implementation of the treatment action
Last evaluation date | Date of last evaluation of the residual risk
Comment | Place for any additional related comments (for example description of relation between different risks)

## Risk register
Choose Classification
Risk register
| Risk identifier | Risk area (scope of risk) | Risk owner | Date of risk identification | Description of the risk | Risk cause | Threat | Risk analysis and consequences | Date of risk analysis and evaluation | Inherent risk likelihood (1-5) | Inherent risk magnitude/impact (1-5) | Overall inherent risk rating | Updated overall inherent risk rating (manual override) | Type of treatment action | Risk treatment description | Owner of the treatment action | Deadline for action | Residual risk description | Residual risk likelihood (1-5) | Residual risk magnitude/impact (1-5) | Overall residaul risk rating | Following steps description | Last evaluation date | Comment
| 1 | Business process | Department Manager | 2022-02-22 | Risk of unauthorized access to the files | Lack of controls in place | Data loss | Due to the fact that anyone can access general ledger there is consistent high possibility of data loss. | 2022-02-23 | 4 | 4 | High | N/A | Risk Mitigation | Implement controls which will prevent unauthorized access to the general ledger | Department Manager | 2022-02-28 | There will still be a risk of making unauthorized changes (in purpose or by accident). | 1 | 5 | Low | Monitor implementation of the controls and residual risk | 2022-02-23 | N/A
| 2 | IT assets | IT Security Manager | 2022-03-10 | Unauthorized access to sensitive systems or data through phishing emails | Lack of user awareness and education about phishing threats | Data breach | Phishing attacks can lead to stolen credentials, resulting in unauthorized access to systems and data breaches. | 2022-03-11 | 5 | 5 | High | N/A | Risk Mitigation | Conduct regular phishing simulation exercises, provide user awareness training, and implement MFA. | IT Security Manager | 2022-04-15 | Sophisticated phishing attempts may still bypass initial defenses. | 2 | 3 | Medium | Continue regular monitoring of phishing campaigns and adjust employee training as needed. | 2022-04-11 | N/A
. | 3 | IT assets | IT Director | 2022-03-15 | Ransomware encrypts critical data, demanding payment for decryption | Inadequate patch management and weak endpoint security controls | Operational disruption and data loss | Failure to protect systems from ransomware can result in loss of business-critical data and reputational damage. | 2022-03-17 | 4 | 5 | High | N/A | Risk Mitigation | Implement patching, use endpoint detection, and regularly back up critical data. | IT Security Team Lead | 2022-05-01 | Some risk remains due to evolving ransomware tactics. | 2 | 4 | Medium | Periodically review and update backup and recovery plans; conduct penetration testing. | 2022-05-05 | N/A
. | 4 | Personnel | HR Manager | 2022-03-20 | Disgruntled employees may intentionally leak or misuse information | Lack of employee monitoring and access controls | Data breach and financial loss | Insider threats can lead to the compromise of intellectual property or unauthorized changes to systems. | 2022-03-22 | 3 | 4 | Medium | N/A | Risk Mitigation | Implement access controls, conduct regular training, and audit employee access. | HR Manager | 2022-04-30 | Some risk remains if employees bypass access controls. | 2 | 3 | Low | Periodic monitoring and access review. | 2022-05-01 | N/A
. | 5 | IT assets | IT Infrastructure Manager | 2022-04-01 | Failure to apply security patches in a timely manner | Inefficient patch management processes | System compromise and data breach | Unpatched systems can be exploited, leading to unauthorized access and data theft. | 2022-04-03 | 4 | 4 | High | N/A | Risk Mitigation | Implement patch management and conduct regular vulnerability assessments. | IT Infrastructure Manager | 2022-04-15 | Some risk remains due to delays in third-party software patches. | 2 | 4 | Medium | Review patch management processes regularly. | 2022-05-05 | N/A

## Heat map
Choose Classification
Inherent risk register heat map | [6 empty] | Residual risk register heat map
Risk impact | Critical | 0 | 0 | 0 | 1 | 1 | Risk impact | Critical | 1 | 0 | 0 | 0 | 0
| High | 0 | 0 | 1 | 2 | 0 |  | High | 0 | 2 | 0 | 0 | 0
| Medium | 0 | 0 | 0 | 0 | 0 |  | Medium | 0 | 2 | 0 | 0 | 0
| Low | 0 | 0 | 0 | 0 | 0 |  | Low | 0 | 0 | 0 | 0 | 0
| Very low | 0 | 0 | 0 | 0 | 0 |  | Very low | 0 | 0 | 0 | 0 | 0
|  | Very low | Low | Medium | High | Critical |  |  | Very low | Low | Medium | High | Critical
|  | Risk likelihood | [6 empty] | Risk likelihood

## Overall risks
Choose Classification

## Summary of risks (hidden)
Inherent risk |  | Residual risk
Critical | 0 | Critical | 0
High | 4 | High | 0
Medium | 1 | Medium | 3
Low | 0 | Low | 2
Very Low | 0 | Very Low | 0